# Introduction: How to Use This Tool

To be successful, agile projects require a consistent management process. This template provides the various roles involved in agile projects (especially those with limited agile experience) with a comprehensive checklist that ensures that they complete the essential tasks from planning to deployment.  Add tasks or change terminology to align the Checklist with your organization’s approach. As each step is underway, indicate the completion status and add comments to clarify the status.

Phases included in the Checklist and their time relationship:

Project Initiation

Release

For each Sprint

## Phase: Project Initiation. Product Owner is responsible for ensuring tasks are completed

(Before sprint starts)

| Task | Description | Status (pending/in progress/ done) | Comments |
| --- | --- | --- | --- |
| Gather product backlog from stakeholders (should be in the form of stories or epics) | The list of processes to be developed for a project should be in the form of stories or epics, (often derived from use cases or process walkthroughs) |  |  |
| Present overall project goals to user participants | The overall goals will guide the overall shape of the solution and guide the priority-setting for various processes |  |  |
| Identify team members | The members of the project team who will participate in all of the sprints in the project. Include stakeholders, quality assurance and implementation team members. |  |  |
| Identify the key team roles | Scrum master (organizes team, removes blockers, executes on scrum process - sprint planning, retrospectives, daily scrums). - Product owner (communicates with stakeholders, maintains product backlog, prioritizes releases and sprints, completes demo). - Developers and Quality Assurance - Stakeholders. |  |  |
| Define communication plan for community of stakeholders | Identify the expected level of stakeholder participation and get commitment for those resources and time. Identify the method of communication with stakeholders. |  |  |
| Define backlog stories derived from epics | Stories include: - Title - Description (As a <ROLE> I want to <ACTION> so I can <PURPOSE>) - Acceptance Test Criteria (Implementation conditions must be true for the story to be considered complete) |  |  |
| Prioritize backlog and communicate sprint release goals with stakeholders | Prioritize the stories based on user value as communicated by the stakeholders. |  |  |

## Phase: Sprint Planning. Scrum Master is responsible for ensuring tasks are completed

(Before sprint starts)

| Task | Description | Status (pending/in progress/ done) | Comments |
| --- | --- | --- | --- |
| Define sprint lengths | The Scrum Master must establish the length of a sprint (usually one or two weeks). |  |  |
| Present stories and acceptance test criteria | The product owner should lead the team through the proposed project. |  |  |
| Define “done” for each story | Scrum Master and QA to sit with developer to confirm the scope, expectations (acceptance criteria), and technical implementation details for the Sprint, and establish how and how much QA will be carried out, what documentation will be prepared and by whom. |  |  |
| Estimate stories | Product owner/developer/scrum master estimate time for completion of each user story and tasks. Include a provision for non-project activities. |  |  |
| Develop Scrum Board | The scrum master should prepare this project tracking tool. |  |  |
| Book daily scrums | Block off team calendars for the daily scrums, 15 minutes every day. |  |  |

## Phase: Daily Scrums. Scrum Master is responsible for facilitating; all team members attend

## (15 minutes daily)

| Task | Description | Status (pending/in progress/ done) | Comments |
| --- | --- | --- | --- |
| Select story for development and design each story solution | Before developers begin working on a selected story, Product Owner, Technical Architect discuss design elements for that story. |  |  |
| Update status of stories | Identify stories that will be worked on or are in progress. Get time spent and time remaining. |  |  |
| Identify, track, and resolve blockers | Record type of blockers and time spent on each type to improve future estimates. |  |  |
| Calculate time still required for the sprint | Burn down "Done" stories using a Burn down chart. |  |  |

## Phase: Sprint Retrospective. Scrum Master is responsible for ensuring all tasks completed

## (The entire team participates at the end of each sprint)

| Task | Description | Status (pending/in progress/ done) | Comments |
| --- | --- | --- | --- |
| Review sprint status | Review stories in the sprint: what was completed, what was not, what will be demoed, what will be released. |  |  |
| Discuss what was done well, areas for improvement, changes required to improve results | Encourage open discussion to identify parts of the process that would benefit from change. |  |  |
| Agree on how the next sprint will be run | Make adjustments to make the sprint process more effective. |  |  |

## Phase: Demo. Product Owner is responsible for ensuring all tasks completed

## (At end of each sprint)

| Task | Description | Status (pending/in progress/ done) | Comments |
| --- | --- | --- | --- |
| Execute demo | Carry out the demo to relevant stakeholders. |  |  |
| Gather feedback | Collect detailed comments from all observers, consolidate findings. Add to project backlog. |  |  |
| Discuss stories that will be completed in the upcoming sprint | Review the stories planned. |  |  |

## Phase: Product and Sprint Release. Product Owner is responsible for ensuring all tasks completed (At end of each sprint)

| Task | Description | Status (pending/in progress/ done) | Comments |
| --- | --- | --- | --- |
| Communicate to stakeholder community | When the contents of a sprint are ready for deployment, inform the user population of the changes in the systems, include Help Desk. |  |  |
| Provide training | Provide training for the new functionality to the stakeholder community, including Helpdesk. |  |  |

_____________________________________________________

Info-Tech Research Group tools and template documents are provided for the free and unrestricted use of subscribers to Info-Tech Research Group services. These documents are intended to supply general information only, not specific professional or personal advice, and are not intended to be used as a substitute for any kind of professional advice. Use this document either in whole or in part as a basis and guide for document creation. To customize this document with corporate marks and titles, simply replace the Info-Tech Information in the Header and Footer fields of this document.