## Project Capacity View
[7 empty] | Each line on the graph represents a different kind of resource. As you add projects, the number of people you have vs. the amount of work they have to do will change. By playing with the settings on this page, you can answer the following questions: How many resources do I really need to get all of these projects done? What happens if one of my projects is late by a week? What happens if I lose someone mid-project? Play with it and see what happens! | [6 empty] | Quick and Dirty Capacity Tool
MOVE your projects back and forth through time with the slider buttons.
You can also change the project durations (in weeks), and the number of each type of resource needed on the project.
[7 empty] | Capacity Table | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
[7 empty] | Business Analysts | 16 | 28 | 10 | 32 | 14 | 14 | 26 | 10 | 14 | 6 | 4 | 4
[7 empty] | Developers | 0 | 0 | 28 | 24 | 24 | 34 | 34 | 6 | 56 | 34 | 6 | 6
[7 empty] | Testers | 2 | 2 | 2 | 18 | 10 | 16 | 22 | 32 | 40 | 14 | 24 | 24
[7 empty] | Capacity | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48
Start | Project | Duration |  |  |  |  | Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | Resource | Qty. Needed | Start | End | bar: 1 to 5
1 | Project 1 | 5 | Business Analysts | 2 | 1 | 1.25 | Requirements | bar: 1
|  |  | Developers | 2 | 1.25 | 2.5 | Design | bar: 2
|  |  | Testers | 1 | 2.5 | 3.75 | Build | bar: 3
[5 empty] | 3.75 | 5 | Test | bar: 4 to 5
[6 empty] | R | Business Analysts | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | D | Business Analysts | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | B | Business Analysts | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | T | Business Analysts | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | S | Business Analysts | 16 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 28 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 2 | 0 | 2 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Start | Project | Duration |  |  |  |  | Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | Resource | Qty. Needed | Start | End | bar: 2 to 7
2 | Project 2 | 6 | Business Analysts | 3 | 2 | 2.5 | Requirements | bar: 2
|  |  | Developers | 2 | 2.5 | 4 | Design | bar: 3 to 4
|  |  | Testers | 1 | 4 | 5.5 | Build | bar: 4 to 5
[5 empty] | 5.5 | 7 | Test | bar: 6 to 7
[6 empty] | R | Business Analysts | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | D | Business Analysts | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | B | Business Analysts | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | T | Business Analysts | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
[6 empty] | S | Business Analysts | 0 | 24 | 6 | 12 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 20 | 20 | 4 | 4 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 2 | 0 | 2 | 2 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Start | Project | Duration |  |  |  |  | Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | Resource | Qty. Needed | Start | End | bar: 4 to 9
4 | Project 3 | 6 | Business Analysts | 2 | 4 | 4.5 | Requirements | bar: 4
|  |  | Developers | 3 | 4.5 | 6 | Design | bar: 5 to 6
|  |  | Testers | 4 | 6 | 7.5 | Build | bar: 6 to 7
[5 empty] | 7.5 | 9 | Test | bar: 8 to 9
[6 empty] | R | Business Analysts | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | D | Business Analysts | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0
[6 empty] | B | Business Analysts | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | T | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 0 | 0 | 0
[6 empty] | S | Business Analysts | 0 | 0 | 0 | 16 | 4 | 8 | 4 | 4 | 4 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 6 | 6 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 8 | 0 | 8 | 8 | 32 | 32 | 0 | 0 | 0
Start | Project | Duration |  |  |  |  | Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | Resource | Qty. Needed | Start | End | bar: 8 to 10
8 | Project 4 | 3 | Business Analysts | 1 | 8 | 7.75 | Requirements
|  |  | Developers | 2 | 7.75 | 8.5 | Design | bar: 8
|  |  | Testers | 1 | 8.5 | 9.25 | Build | bar: 9
[5 empty] | 9.25 | 10 | Test | bar: 10
[6 empty] | R | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | D | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
[6 empty] | B | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | T | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
[6 empty] | S | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8 | 0 | 0
Start | Project | Duration |  |  |  |  | Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | Resource | Qty. Needed | Start | End | bar: 7 to 12
7 | Project 5 | 6 | Business Analysts | 2 | 7 | 7.5 | Requirements | bar: 7
|  |  | Developers | 3 | 7.5 | 9 | Design | bar: 8 to 9
|  |  | Testers | 3 | 9 | 10.5 | Build | bar: 9 to 10
[5 empty] | 10.5 | 12 | Test | bar: 11 to 12
[6 empty] | R | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
[6 empty] | D | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0
[6 empty] | B | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 0
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | T | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24
[6 empty] | S | Business Analysts | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 4 | 8 | 4 | 4 | 4
[7 empty] | Developers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 6 | 6
[7 empty] | Testers | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 6 | 24 | 24

## Set Your Assumptions Here
Use this page to set the assumptions for your project capacity view. These don't have to be exact. Just enough for you to get a gauge on how your projects will likely interact as they slide over top of one another.
Assumptions:
All projects follow a standard SDLC waterfall methodology.
The requirements phase makes up | 25% | of the duration of a project and is composed of:
|  | Business Analysts who work | 100% | of a business day, or | 8 | hours per day
|  | Testers who work | 25% | of a business day, or | 2 | hours per day
The design phase makes up | 15% | of the duration of a project and is composed of:
|  | Business Analysts who work | 25% | of a business day, or | 2 | hours per day
|  | Developers who work | 75% | of a business day, or | 6 | hours per day
The build phase makes up | 20% | of the duration of a project and is composed of:
|  | Business Analysts who work | 25% | of a business day, or | 2 | hours per day
|  | Developers who work | 100% | of a business day, or | 8 | hours per day
The test phase makes up | 40% | of the duration of a project and is composed of:
|  | Business Analysts who work | 25% | of a business day, or | 2 | hours per day
|  | Developers who work | 25% | of a business day, or | 2 | hours per day
|  | Testers who work | 100% | of a business day, or | 8 | hours per day
For a total of | 100% | of the project.
There are | 2 | Business Analysts |  | each with a capacity of | 8 | hours per day | for a capacity of | 16 | hours.
| 2 | Developers |  | each with a capacity of | 8 | hours per day | for a capacity of | 16 | hours.
| 2 | Testers |  | each with a capacity of | 8 | hours per day | for a capacity of | 16 | hours.