<Client>

Intranet Planning Project

<MM/DD/YYYY>

DRAFT

Executive Summary	3

1. Introduction	3

1.1. Process followed	4

2. Findings	4

3. Recommendations	5

3.1. Development Efforts	5

3.2. Design Considerations	5

3.3. Risks/Concerns	5

4. 4. Intranet Content	6

4.1. Content Types	6

4.2. Sales Force Requirements	7

4.3. Content Management	7

4.4. Content Security	8

5. Infrastructure	8

5.1. The Network	8

5.2. The Server	10

5.3. The Client	10

5.4. The Development Environment	11

5.5. Current Applications Architecture	11

6. Next Steps	12

6.1. Priorities and Action Items	12

6.2. Project Plan	12

6.3. Futures	12

6.4. Risks/Issues	13

Appendix A - Interview Results	14

Appendix B - Project Schedule	22

Appendix C – Intranet Development Considerations	25

Appendix D - Factory Locations	36

Executive Summary

Introduction

The Intranet Planning Project focused on developing a long-term design and development plan for CLIENT’s Intranet system coordinated with the Sales Force Automation initiative.

In addition to reviewing the current technical environment and interviewing end users, the team developed a detailed work plan and budget to address the highest priority concerns of the initial target group – the <Client> sales force.

An Intranet is essentially a private communications network.  It utilizes the same technologies that make the Internet a useful tool across multiple computer platforms and around the world.  These technologies allow for rapid development and deployment of data and applications throughout an organization.  In the case of the <Client> sales force, it will allow these personnel improved access to current information and facilitate communications for more informed business decisions.

Process

The project team conducted a series of interviews with <Client> personnel for input and ideas on the information and functionality necessary for them to make more informed business decisions.  The goal of this effort was to identify areas of improvement that could be prioritized to provide the greatest return on investment possible.  The interviews also served to help promote awareness of the Intranet efforts and potential capabilities to future users.

Findings

In this phase, the team focused specifically on the sales group.  Targeted capabilities for the first phase of the Intranet implementation are:

- E-mail – access to GroupWise mail for enhanced communication ability.

- Newsletter - On-line access to the weekly newsletter containing delivery schedules, new merchandise, etc.

- Order information - Access to inventory and order status currently only available through the AS/400 system.

The implementation phase will develop and deploy the infrastructure and framework necessary to provide not only the sales force, but also the entire company, benefits from increased access to information and application systems.  The design began on January 27, with the first phase deployment expected to be complete by April 1, 1997.

- Introduction

Initiation of the Intranet Planning Project began on January 2, 1997.  This was a three-week planning project completed on January 24, 1997.  The driver of the project in the initial stage was the Sales Force Automation effort.  Automation includes email, on-line catalogs, inventory updates, form submittal and other items.  The secondary intent of the project was planning for other areas of the company in later phases, e.g., factories and human resources.

Rollout of the Sales Force Automation Intranet begins in April 1997.  This rollout will establish the network, hardware and software necessary for support of the Intranet.  In support of this effort, three separate projects are also underway:

- Upgrade to GroupWise 5		Estimated completion May 1997

- Client/server E-mail system that includes workflow and document management capabilities.

- Upgrade to Windows 95		Estimated completion July 1997

- Updated operating system to simplify and enhance client networking capabilities.

- Deployment of ManageWise	Estimated completion August 1997

- ManageWise integrates server management; desktop management; network traffic analysis; automated network inventory; remote control capabilities; virus prevention and software management.

These projects will help assemble the infrastructure needed to efficiently and effectively deploy and manage an Intranet.

The essential element of an Intranet that was required for this effort was accessibility.  Personnel require only limited software and hardware to reach the Intranet from anywhere in the world.  Sales staff and other remote users will be provided with dial-in connections.  Permanent sites such as remote factories and sales offices will make use of dedicated lines.

  - Process followed

The CONSULTANT Intranet development process specifies four distinct phases

- Discover		Collect and review information.

- Design		Plan and construct the Intranet.

- Implement	Make it a reality.

- Launch		Make it available.

The collection and analysis of information occurs in the Discover phase.  This information, in the form of user interviews and wish lists is used to fuel the design phase.  The design stage produces two types of deliverable, the system architecture and the plans to implement and support that architecture.  Deployment of initial content on the newly created system occurs during implementation.  The final process is the launch where the system is promoted within the company and provided for general use.

- Findings

A series of interviews were conducted with a cross section of <Client>  personnel.  Primarily, these discussions were intended to solicit ideas and input for information necessary to effectively perform their job responsibilities in an Intranet environment. The team was also able to promote awareness of these efforts to the people that could benefit the most from the easily accessible information.

Sales personnel are the primary focus of the first phase of the Intranet - Sales Force Automation.  As can be expected, each sales group has special concerns specific to their particular needs.  For example, international personnel are especially concerned with communications.  Obtaining and providing information is much more difficult for them than for domestic staff.  In addition, national account staff are concerned with understanding the status of their automated orders and sharing this knowledge with their customers.  The entire sales staff we interviewed was unanimous in their request for access to both the newsletter and inventory status.

In addition to the sales area, the following groups were also interviewed: Engineering, Maintenance, Accounting, Business Automation, Administrative Staff, Customer Service, Information Systems, Distribution, Personnel, Advertising and Marketing.  Many of these representatives provided suggestions for content documented in section 4.  Appendix A documents the list of interviews, attendees, and notes.

- Recommendations

  - Development Efforts

CONSULTANT recommends that <Client> proceed immediately with production of the Sales Force Automation Intranet.  The benefits of simplified access to more accurate information and the ability to facilitate communications between people can only improve bottom line results.  Before user interest wanes and the project loses momentum, we believe that the Intranet team must act on the findings in the Discovery phase by providing tangible results to the sales force.

As part of the initial Intranet launch, we suggest that more extensive functionality be considered.  Based on the timeframe involved, our team believes that they can provide more extensive information content than the core requirements established during interviews with the sales personnel.  Basic information such as phone lists or delivery schedules could be provided as well.

Later stages should provide content for the remaining areas and more complex information types for sales and other staff.  Interactive applications such as time and expense reporting could be developed or purchased.  Allowing key customers to access their order and delivery status may be desirable in the future as well.

  - Design Considerations

Management of content will occur in three tiers, comprising two levels of oversight, with content producers publishing their own Intranet content.  Current data maintenance activities will be leveraged to minimize the creation of new work.

  - Risks/Concerns

Very few of the Internet/Intranet tools on the market support the NetWare WebServer at this time.  It is likely that this situation will soon be remedied but it should be monitored.  Unless both Novell and third-party application support increases for IntranetWare by mid to late 1997, <Client> should consider integrating existing Intranet development efforts with a more widely supported platform such as Windows NT or UNIX.  For example, the NDS security scheme could work with both Novell and Windows NT and help secure the initial investment while maintaining options on other platforms.  For the long term, it will be more efficient and cost effective to rely on packaged software solutions and well-supported platforms.

- 4. Intranet Content

  - Content Types

The following table lists the broad types of content requested for the Intranet including the estimated phase of implementation.

| Phase | Category | Description |
| --- | --- | --- |
| 1 | Email | Provide remote access to GroupWise. |
| 1 | Directory access | Provide remote access to network files. |
| 1 | General information | Access to information on employees including schedules, telephone lists, work locations, departments, etc. as well as office locations. |
| 1 | Sales access to JBA | Allow salesman and other staff to enter orders, check order status, and query stock inventory. |
| 1 | Clothing catalog | Provide electronic access to the clothing catalog. |
| 1 | Newsletter | Provide electronic access to the newsletter. |
| 1 | Notifications | Disseminate notifications to staff quickly. |
| 1 | 3rd Party Shipping information | Provide access to exterior web sites to track shipping, e.g., RPS, UPS, and FedEx. |
| 2 | AS/400 Access | Provide access to the AS/400. |
| 2 | Project Folder | All project folder material including garment specifications, designs, etc. Covers information from many departments. |
| 2 | Corporate information | Access to operating procedures and company policies. |
| 2 | IS information | Place computer manuals and Information Systems guidelines on-line as well as functional and technical specifications. |
| 2 | Transportation information | Access to information from transportation sources such as trucking schedules, picking, packing, billing, and trucks received. |
| 2 | Electronic forms | Allow staff to submit and track requests, e.g., purchase orders, maintenance requests, status and expense reports, inventory transfers, help desk requests and problem reports. |
| 2 | Marketing and Advertising information | Access to information from the marketing and advertising departments on trade show calendars, promotions, contests, etc. |
| 2 | Sales information | Access to information collected by sales staff such as call reports as well as information on salesman addresses and territory lists and sales commissions. |
| 2 | Electronic reports | Provide electronic reports used by multiple staff, e.g., Schedule S-3, Gross Profit, Gross Position, Quarterly sales and Inventory reports. |
| 2 | HR information | Access to information from the human resources department including new hire lists. |
| 2 | Accounting information | Access to information from the accounting department including the fiscal calendar. |
| 2 | Outlet store information | Access to information from and about outlet stores including SKU numbers, and reduce lists. |
| 3 | Engineering information | Access to information from engineering staff on physical plant inventory. |
| 3 | CBT courses | Provide access to computer based training courses. |
| 3 | OLAP | On-Line Analytical Processing of customer and sales data. |
| 4 | Customer access | Allow customers to access specific information. |

  - Sales Force Requirements

The Intranet planning interviews identified three desired requirements.  These items are targeted for the initial Sales Force Automation implementation. .

- E-mail.  All personnel need access to e-mail.  GroupWise WebAccess or GroupWise Remote can provide this capability.  GroupWise WebAccess does not provide the full functionality of GroupWise Remote but the web browser interface will be simple to learn, will not require additional software, and should meet the majority of staff needs.

- Newsletter.  The information provided in the publication needs to be updated daily and available online through the Intranet.  Publication and distribution of currently occurs weekly.  Individuals responsible for the content in the refresh it on a weekly or longer period.  Only specific types of information, such as delivery schedules, change more frequently.

- Order/Inventory Status.  Provide the sales force with current inventory levels from the AS/400.  The Intranet can provide access to the JBA applications.  This would require training for the sales staff on the AS/400 and the JBA applications.  An alternative may be to develop some simple front-end programs to access the AS/400 data through an Oracle gateway.  This could reduce the training requirements and provide a more secure way to access the data as well.  This mechanism is preferred for individuals with limited computer training.

  - Content Management

In order to reduce workloads while still providing content control, three layers of personnel will manage content through the following roles:

- Webmaster - Responsible for the entire Intranet.  Determines Intranet direction and implements all policy changes.  Will work closely together with Content Managers to insure that the Intranet meets the requirements of the organization and is well maintained.

- Content Manager - One to manage each broad area of content, e.g., sales.  The Content Managers insure that the content in each area is updated and maintained in a timely fashion and a useful format.

- Content Developer - Individuals currently responsible for specific information and will provide that information as Intranet content.

Content Managers and Developers should be appointed from each user department that has data to be published on the Intranet.  The distribution of work involved in publishing the information should be as wide as possible to reduce the amount of effort individuals must perform to keep the information current.  Toward this end, individual developers will post information to the Intranet as it is created or updated.  Wherever possible, posted information will remain in the same format as it was created.  Where native document formats are not acceptable, posting standards are not adhered to, or other problems occur, the Content Manager will be responsible for placing the information in the proper format.

  - Content Security

All Intranet content will be secured using normal HTTP Basic authentication consisting of user ids and passwords.  User Ids and passwords will be authenticated against current NetWare IDs using existing Novell NDS security features.  If required, Secure HTTP and Secure Socket Layer encryption will also be activated.  In the initial phase, existing WebServer and Novell security should be sufficient.  Existing security monitoring and logging will be supplemented with custom CGI scripts.

Content intended for specific users or groups will be restricted using existing web server security mechanisms.  These mechanisms allow static pages to be restricted based on directory location and data type.  A standard security check framework will be created for NetBasic CGI programs based on an extension of the existing access control files.

- Infrastructure

  - The Network

The internal network infrastructure is already in place and functioning within most locations.  Two vendors are currently preparing proposals for connecting <Client> sites together with a private Intranet with Internet connectivity.  They are IBM Global Services and AT&T WorldNetSM Intranet Connect Service (ICS).  They both can provide a managed secure network that would allow intra-company communications without allowing outside Internet traffic in.  Using a managed network vendor will allow <Client> to quickly implement a secure solution without purchasing additional networking hardware and hiring support personnel to manage it.

Two separate network architectures are currently under consideration.  In the short-term, a managed network vendor will provide complete support of wide-area connections through a private Internet.  The managed network vendor will also provide all hardware required for connecting local networks at each site.  Full support will be provided for this hardware and the connecting wide-area network.  Under this architecture, it is not possible for network traffic from the general Internet to reach any machines on the local network.  Outbound network traffic can still exit the private Internet to reach the public Internet.

Over the long term, the public Internet traffic will be removed from the private Internet and routed through the <Client> General Office.  Public Internet traffic will be able to exit and enter the local network by travelling through a firewall supported by <Client> personnel.  Expanding the network in this fashion increases Internet flexibility and reduces public Internet costs.

  - The Server

Novell IntranetWare is the basis for the software suite chosen to implement the Intranet.  The IntranetWare WebServer is currently in version 2.5.  Release of version 3.0 of the WebServer is due before the April timeframe and will provide support for secure communications and Oracle database access.  Using the Novell software will aid in leveraging currently installed products while facilitating a rapid implementation schedule.

The hardware to be used is a Compaq Proliant 2500 rack-mount server that has already been purchased and installed.  It has a Pentium Pro 200 MHz processor, 256 MB of RAM, 20 gigabytes of disk space, and fast Ethernet networking capabilities.

  - The Client

TI TravelMate laptops being issued to the sales force will be configured with the following software:

| Operating System | Microsoft Windows 95 |
| --- | --- |
| Application Suite | Microsoft Office 97 Standard: - Word - Excel - PowerPoint |
| Web Browser | Netscape Navigator 3.0 (Novell version) |
| Virus Protection | Norton Anti-Virus |

  - The Development Environment

The selected components for the Intranet develop environment are:

- HiTecSoft’s NetBasic WebPro - a scripting language for developing Intranet applications and utilities that run directly on NetWare file servers.  The NetBasic language from HiTecSoft was the choice for Oracle access and program development.

- Microsoft FrontPage 97 - a web authoring and management tool that will help simplify web page publishing and provides page layout design capabilities.

- Microsoft Office 97 suite - can be used to help supplement Intranet content by saving word processing documents, spreadsheets, graphics, and databases as web pages.

- The AS/400 Workstation Gateway - an option that can be used to allow existing AS/400 applications to run on the web for those that need that access.

  - Current Applications Architecture

Current data and applications will be utilized in order to support the requirements of an Intranet.  The following table lists the major hardware platforms and the applications they host.

| Platform | Applications |
| --- | --- |
| IBM AS/400 | Accounting (AR, AP, GL) Order Entry Warehousing Inventory Sales Analysis (Planned) Customer Returns Forecasting |
| IBM Mainframe | Manufacturing/Distribution EDI Human Resources/Payroll Report Distribution |
| IBM RS/6000 | Distribution Center |
| Novell Network | Imaging (Dataplex is Service Provider) Risk Assessment (D&B) Balance Reporting (Service from NationsBank & Core States) RPS Status Report (Dial-out application similar to FedEx) Microsoft Office Rumba Terminal Emulation Warehouse Packing and Shipping Expected Receipts from Factories |

- Next Steps

  - Priorities and Action Items

In rough order of priority, the following is a list of action items required at the start of the next phase of work.

- Begin design of Intranet

- Choose an Internet Service Provider

- Provide laptops and training to salesmen

- Purchase remaining software

- Install Intranet server and software

- Upgrade to GroupWise 5

- Upgrade to Windows 95

  - Project Plan

The proposed project plan for designing, implementing and fielding the Sales Force Automation Intranet is based on the CONSULTANT WebWave Intranet Development plan.  The project is scheduled to begin on January 27, 1997 and end on March 27, 1997.  Appendix B lists the tasks required for completing the project.  The two primary groups of tasks, Design and Implementation, are intended to run in parallel.

With the exception of NetBasic from HiTecSoft (<$10,000 per server) and the selection of the Internet Service Provider, all major purchases were made prior to, or during the planning stage.

  - Futures

The scope of the Sales Force Automation Intranet was intentionally restricted to allow for rapid development and deployment.  These elements will become important to the Intranet in the long-term.  In addition, some elements chosen to aid in the implementation were selected for availability and not for their long-term viability.

Several areas will be of interest in future development:

- Packaged software.  The Intranet is a rapidly evolving area of technology.  It is just now leaving its infancy and entering the packaged software stage.  <Client> should concentrate Intranet development around software packages and not on custom developed software.

- Electronic commerce.  Personnel have expressed interest in allowing customers to submit and track orders electronically through the Internet.  In order to support this with security and reliability, Internet commerce servers are required.

- Electronic workflow and groupware applications.  These applications support more complex communications and speed work.  Functions of these products cover: message conferences, voice and video conferencing, routing and version control of documents and projects, and other group activities.

- Integration with existing software.  Intranets and general application software are growing toward a common point.  It is important to choose a path that minimizes the cost and difficulty of reaching this goal.  Even in the short-term, the process for creating and maintaining content on the Intranet can be eased and simplified by choosing Intranet and application software that coexists well.

  - Risks/Issues

Novell applications are the basis for all of the Intranet server software chosen for the first phase.  The network operating system is Novell's IntranetWare, the web server is Novell's WebServer and Novell licenses the CGI programming environment.  This makes for a tight binding between all the applications and one-stop shopping for support.  Unfortunately, Novell is not yet widely supported by third party Intranet software developers.

The application suite chosen for general use at <Client> is Microsoft Office 97.  This application suite has nascent Intranet support.  This covers both static and dynamically changing content.  The dynamic content requires the use of Microsoft's Internet Information Server (IIS) running under Windows NT.

The web development tool chosen is Microsoft's FrontPage 97.  While there are no server extensions for FrontPage currently available for Novell’s WebServer, there is a Web Publishing Wizard that simplifies publishing web documents.

Most packaged Intranet applications currently require web servers from vendors such as Microsoft and Netscape that support the Win-CGI interface.  Some examples would include software to support newsgroup style forums or continuous news broadcasting.  The most widely supported platform is Windows NT.  If Novell adds support for Win-CGI it will significantly enhance the options available.

Appendix A - Interview Results

| Area | Engineering |
| --- | --- |
| Date | 1/6/97, 1:00 p.m. |
| Attendees | M. Smith |
| Notes | The team conducted a telephone interview with Smith of the engineering department. He was in Mexico at the time. M identified the following major types of specification information as needed by/from the factories: Construction Make Sheets (Word Processing documents) Label Locations (WP documents) Bale Packing Specs (WP documents) SAH (Standard Allowable Hours) (dBASE IV) Thread Specs (dBASE IV) Lot Specs (Mainframe) Changes are made weekly and multiple copies need to be distributed to 20 locations (12 plants, 8 contractors). The factories are not currently using e-mail. They are primarily sending out paper memos. File transfers are accomplished via remote e-mail now. Payroll information is printed out and sent to Ft. Worth to be re-entered. |

| Area | Core Team |
| --- | --- |
| Date | 1/6/97, 3:00 p.m. |
| Attendees | K. Smith, Director of Business Automation |
| Notes | System access to reports and sales orders is needed. JBA's direction is to move toward Client/Server and the Internet (Version 4.0). JBA system documentation and operating procedures could be placed on a web site for easy access. Shop floor information from the plants could be fed back into the AS/400 systems. Remote e-mail. Order status, shipping details, order details for major customers, Wal-Mart, K-Mart, etc. There is a direction toward Vendor Managed Inventory (VMI). Reduction of communication line costs could be a benefit. JBA implementation timeline is 1.5 to 2 years. 15 manufacturing plants goings to LeadTech for plant automation Another 15 to 18 months to implement LeadTech (10 to 15 contractor plants - won’t implement LeadTech) Approx. 150 users on AS/400, have had 200 users at once International users don’t have email access |

| Area | Merchandising, Planning, and Design |
| --- | --- |
| Date | 1/7/97, 8:30 a.m. |
| Attendees | A. Smith B. Smith C. Smith, etc. |
| Notes | Plant connections are needed, especially outside U.S. Access to truck schedules. Distribution of specifications to the factories. File transfers, e.g. UPC labels Procedures Project folder process CAD files Internet Access |

| Area | Engineering and Maintenance |
| --- | --- |
| Date | 1/7/97, 1:00 p.m. |
| Attendees | 2 people |
| Notes | Specifications to the factories, hardcopies are mailed out currently. Inventories of spares and availability: - Equipment surplus. - Fixtures, air compressors, ovens, boilers. - Office equipment, furniture - computers, software - Remainder (cloth, trim, etc) Scheduling and tracking of: - Equipment requests - Maintenance requests Some requests are phoned in, some are e-mailed. Automation of the project folder process. Purchasing information (approved suppliers, negotiated prices, etc.) Trucking schedules maintained by Person |

| Area | Field Sales & International |
| --- | --- |
| Date | 1/9/97, 9:00 a.m. |
| Attendees |  |
| Notes | International access through the Internet would be very useful. Customer access to newsletter, delivery dates, and catalogs but not other customer information. Would like to update the newsletter every day. Want changes in catalog reflected to sales. Inventory access through AS/400 connectivity. Salesmen do not currently write orders, but likely will in the future. Specification changes Access to inventories of close outs and irregulars. Close outs are included in regular inventory. Irregulars are another file through JBA (#73 on menu). Cost data - should not be available to salesmen but others will need. Very restricted. Needed for international. Maybe a dozen people in the whole company. Spec sheets, Lot specs, and production schedule. Delivery Schedule (Newsletter). E-mail. Stock Availability (AS/400) Order status and shipping status by salesman. Showroom availability Trade shows list (scheduled for the public web site). Really need marketing information. Submitting weekly activity reports and expense reports |

| Area | Sales - National Accounts |
| --- | --- |
| Date | 1/9/97, 2:00 p.m. |
| Attendees |  |
| Notes | Wal-Mart is moving towards Internet access of Retail-Link. Going to need Internet access to get to Wal-Mart system. Want to be part of their virtual store. Product mix by store is currently maintained in a Microsoft Access database. JCPenny is already on the Internet. Sales inventory, Lot #s, e-mail addresses, store sales through POS, Purchase Order information. Booking information - prices and quantities expected. New store database for customer service. EDI orders are currently on the AS/400 and not readily accessible. About 30 companies, approximately 60% of volume using EDI. Order Status, Order Counts, Work wear completion - 10 to 15 weekly reports. Some salespeople have approx. 30 predefined AS/400 queries |

| Area | Sales - Corporate Licensing |
| --- | --- |
| Date | 1/1/0/97, 9:00 a.m. |
| Attendees |  |
| Notes | Internal communications, e.g. GroupWise e-mail. Access to the Newsletter online. Updated AS/400 information - Order counts, order activity. Licensing of brand to 8 or 9 manufacturers. Boots, clothes, etc. |

| Area | Sales |
| --- | --- |
| Date | 1/10/97, 1:30 p.m. |
| Attendees |  |
| Notes | Order inquiry needed for now. Order entry as a future. Mail is slow, faxes are illegible, handwriting errors, rework. Reduced items list published weekly and distributed. Catalogs are out of date. Biggest problem is lag time in information Factory connectivity. Email Newsletter Close outs |

| Area | Administrative Assistants |
| --- | --- |
| Date | 1/14/97, 9:00 |
| Attendees |  |
| Notes | Expense Reports Call Reports S3 Schedule (monthly) from accounting - Expenses and budgets by division. Distribution list to department heads and supervisors. Phone list Budgets Announce new hires Employee list with pictures National and Regional Sales meetings, schedule and planning Salesmen’s address and territory list. Events scheduling (Rodeo, Circus, etc.) |

| Area | Customer Service |
| --- | --- |
| Date | 1/14/97, 1:00 |
| Attendees |  |
| Notes | Salesmen need a simple interface, as easy as possible. Inventory, order, and account information Email 1st rollout is 13 salesman (4 have computer exp.) Warehouses also deal w/salesman and customers Customer satisfaction benchmarking as a possibility. “WC” is the catalog Want better communications - beyond email Conferencing, news server, etc. Want Computer Based Training (CBT) over the Intranet SL190S, SL184 - Sales commission reports to post RPS and UPS shipping data |

| Area | Accounting |
| --- | --- |
| Date | 1/14/97, 3:00 |
| Attendees |  |
| Notes | Consolidated financial statements are sent to auditors. Kept as Excel macros. S3 - monthly reports to all salesmen and sales managers. Produced by accounting in Excel. Fiscal calendar is 4-4-5. Could be posted on an Intranet so people could see period end dates. Cost book - goes to department heads, each gets separate section (high priority) - DB/2 files Payroll and expense reports from JBA by department, to department heads. Notifications to salesmen of payroll changes. Purchase Orders Expense Reports Procedures SL190, SL190S - Commission reports Gross Profit (GP) report done weekly, widely distributed, from mainframe. |

| Area | Information Services |
| --- | --- |
| Date | 1/15/97, 10:00 a.m. |
| Attendees |  |
| Notes | Quarterly salesmen report Functional and technical specifications Incident reports Help desk requests Problem log is an Access database. Remote access for programmers. Graphical presentation of AS/400 data for salesmen. Production schedule 40 WD salesman 11 DIW salesman Control D - report/archival facility, Robot reports |

| Area | Distribution Center |
| --- | --- |
| Date | 1/15/97, 1:00 p.m. |
| Attendees |  |
| Notes | Production reports - weekly, monthly, annual statistics. Order status Picking, Packing, Billing, & Shipped spreadsheets are faxed out to 10-15 different people. Carrier information & order status. Purchase Order information. Transfer Documentation, Inventory Transfer, Transfer Order Form 724 - money transfers. Keeping up with Samples and special cuts. Promotional item inventories, Displays. Point of Sale materials Need schedules of releases of in port shipments (Person maintains). Better access to bales scanned onto trucks, loaded bales from plants. Communicate with Outlet Store MOA - Monthly Order Analysis, carryover by lot of orders in-house. MOR - Monthly Order Report, ordered and shipped by category. (from AS/400) Reduce number of calls for order status. |

| Area | Personnel |
| --- | --- |
| Date | 1/16/97, 1:00 p.m. |
| Attendees |  |
| Notes | Factories need to be able to communicate updates for the Newsletter. Biggest competitor is Red, they allow electronic order submission (use a product called RK On) Outlet store traffic - Newsletter, Reduced list, SKU numbers (Express mail weekly). Final release - last phase of project folder after all sign-offs AR - looking at PC software to manage project folders Discontinued list - sometimes in Newsletter. Access to salesman call reports (activity reports). Access to network files Some access to AS/400 applications Outlet store Sales report and inventory report (Excel spreadsheets). Personnel forms, Policies and procedures 401K, Flex Plan Check request forms (PO requests) Maintenance work requests Hire list and discontinue list from plants Timecards Insurance list - who’s eligible, forms, etc. Cut sheets - production process, goes to the plants Invoices and loaded bale reports coming from the plants (takes almost an hour, 35 pages, for plant to print them off) Invoices are couriered in from plants to prep warehouses for arrival TOR - trim order report, order requests, backorder list |

| Area | Advertising |
| --- | --- |
| Date | 1/17/97, 9:00 a.m. |
| Attendees |  |
| Notes | 8 people on the Internet team. Internet Site graphics all done in-house. Eric and Kelly do the layout for the site. Update the site every 3 weeks. US Network in Addisson does HTML layout and hypertext links. Michelle assembles information into Newsletter. (PhotoShop and Quark) Marketing updates - Advertising schedule Scans of recent ads Contest and promotions information Merchandising area must push certain garments at certain times of the year. Publicize success stories, accounts. News stories come from Internet group - filtered from various sources. Dee in Public Relations - handles garment placements, movie stuff, magazines, etc. |

| Area | Advertising - Newsletter |
| --- | --- |
| Date | 1/20/97, 3:00 p.m. |
| Attendees |  |
| Notes | About a half a day per week spent publishing the Newsletter on Wednesdays. Industrial Department - 2 pages. Content provided by Bill & Darryl. Merchandise Control - Delivery schedules, Dates items available from Sharon. Merchandising - New items from Ann and Craig. Michelle puts together the first two pages. Marketing - FYI every 2 weeks form Jason. Everything comes in on paper. Quark Express (Macintosh) used to publish everything. Bound copy kept every year of all issues. Michelle keeps most recent 2 years. Year-end Newsletter also done. Keep a CD-ROM with all pictures of salesmen and management. Receive everything by Wednesday at 11:00 a.m. Must be printed by Thursday at 2:00 p.m. for salesmen’s mail. |

Appendix B - Project Schedule

| Task | Start Date | End Date |
| --- | --- | --- |
| Establish Design Parameters | Mon. 1/27/97 | Mon. 2/3/97 |
| Determine Constituencies | Mon. 1/27/97 | Mon. 1/27/97 |
| Determine Message for Each Audience | Tue. 1/28/97 | Thu. 1/30/97 |
| Create On-line Geometry | Fri. 1/31/97 | Mon. 2/3/97 |
| Hold Creative Strategy Meeting | Tue. 2/4/97 | Tue. 2/11/97 |
| Brainstorm Themes | Tue. 2/4/97 | Thu. 2/6/97 |
| Create Site Concept | Fri. 2/7/97 | Mon. 2/10/97 |
| Draft Ties Between Visual and Structural Architectures | Tue. 2/11/97 | Tue. 2/11/97 |
| Design Home Page | Wed. 2/12/97 | Tue. 2/18/97 |
| Design Home Page Layout | Wed. 2/12/97 | Fri. 2/14/97 |
| Design Home Page Graphics | Wed. 2/12/97 | Tue. 2/18/97 |
| Refine Concept | Wed. 2/19/97 | Wed. 2/26/97 |
| Conduct Development Team Composition Review | Wed. 2/19/97 | Wed. 2/19/97 |
| Present Concept to Principals | Thu. 2/20/97 | Thu. 2/20/97 |
| Refine Home Page Composition | Fri. 2/21/97 | Tue. 2/25/97 |
| Obtain Concept Sign-off | Wed. 2/26/97 | Wed. 2/26/97 |
| Create Full-Site Comps | Thu. 2/27/97 | Thu. 3/13/97 |
| Design Information Area Layouts | Thu. 2/27/97 | Mon. 3/3/97 |
| Design Information Area Graphics | Thu. 2/27/97 | Wed. 3/5/97 |
| Conduct Development Team Composition Review | Thu. 3/6/97 | Thu. 3/6/97 |
| Present Initial Comps to Principals | Fri. 3/7/97 | Fri. 3/7/97 |
| Refine Information Area Compositions | Mon. 3/10/97 | Wed. 3/12/97 |
| Obtain Information Area Composition Sign-off | Thu. 3/13/97 | Thu. 3/13/97 |
| Prepare Production Graphics and Layout | Fri. 3/14/97 | Thu. 3/27/97 |
| Create Production Pages | Fri. 3/14/97 | Mon. 3/24/97 |
| Run Final Quality Assurance Checks | Tue. 3/25/97 | Thu. 3/27/97 |
| Select Internet Connection Method | Mon. 1/27/97 | Mon. 2/10/97 |
| Design Internet Connection Method | Mon. 1/27/97 | Fri. 2/7/97 |
| Select an Internet Service Provider | Mon. 2/10/97 | Mon. 2/10/97 |
| Design Heritage System Integration | Mon. 1/27/97 | Fri. 3/14/97 |
| Design Heritage System Connection Methods | Mon. 1/27/97 | Fri. 3/7/97 |
| Configure Connections | Mon. 3/10/97 | Fri. 3/14/97 |
| Design Client-side Infrastructure | Mon. 1/27/97 | Mon. 3/17/97 |
| Review Required Functionality | Mon. 1/27/97 | Fri. 3/7/97 |
| Select Client Software | Mon. 3/10/97 | Mon. 3/10/97 |
| Design Software Distribution Scheme | Tue. 3/11/97 | Mon. 3/17/97 |
| Develop Interactive Systems | Mon. 1/27/97 | Wed. 3/12/97 |
| Review Requirements | Mon. 1/27/97 | Fri. 2/14/97 |
| Research Package Solutions | Mon. 2/17/97 | Wed. 2/19/97 |
| Design Custom Solutions | Thu. 2/20/97 | Wed. 3/12/97 |
| Select a Search Engine | Mon. 2/17/97 | Wed. 2/19/97 |
| Select a Collaborative Technology | Mon. 2/17/97 | Wed. 2/19/97 |
| Develop Content Management Plan | Mon. 1/27/97 | Wed. 2/19/97 |
| Document Content Architecture | Mon. 1/27/97 | Fri. 2/7/97 |
| Select Content Management Tools | Mon. 2/10/97 | Wed. 2/12/97 |
| Develop Content Management Policies and Procedures | Mon. 2/10/97 | Fri. 2/14/97 |
| Procure or Develop Content Management Tools | Mon. 2/17/97 | Wed. 2/19/97 |
| Develop Security Plan | Mon. 1/27/97 | Fri. 3/14/97 |
| Document Security Architecture | Mon. 1/27/97 | Fri. 2/21/97 |
| Select Security Tools | Mon. 2/24/97 | Wed. 2/26/97 |
| Design Security Policies and Procedures | Mon. 2/24/97 | Fri. 3/14/97 |
| Procure or Develop Security Tools | Thu. 2/27/97 | Wed. 3/5/97 |
| Develop Monitoring Plan | Mon. 1/27/97 | Fri. 3/14/97 |
| Create Site Access Monitoring Plan | Mon. 1/27/97 | Fri. 3/14/97 |
| Create Site Intrusion Monitoring Plan | Mon. 1/27/97 | Fri. 3/14/97 |
| Create Site Availability Monitoring Plan | Mon. 1/27/97 | Fri. 3/14/97 |
| Develop Training Plan | Mon. 1/27/97 | Mon. 2/24/97 |
| Identify Positions and Staffing Levels | Mon. 1/27/97 | Fri. 2/7/97 |
| Identify Skill Gap | Mon. 2/10/97 | Wed. 2/12/97 |
| Identify Appropriate Vendor Training | Thu. 2/13/97 | Mon. 2/17/97 |
| Develop Custom Training | Tue. 2/18/97 | Mon. 2/24/97 |
| Develop Internal Promotion Plan | Mon. 1/27/97 | Fri. 3/21/97 |
| Set Objectives | Mon. 1/27/97 | Fri. 3/7/97 |
| Develop Sponsor List | Mon. 3/10/97 | Fri. 3/14/97 |
| Design Promotional Activity | Mon. 3/17/97 | Fri. 3/21/97 |
| Install Hardware and Software | Mon. 1/27/97 | Mon. 2/17/97 |
| Configure Hardware Components | Mon. 1/27/97 | Fri. 2/7/97 |
| Install & Configure Server Software | Mon. 2/10/97 | Wed. 2/12/97 |
| Install/Configure Content Management Server Support | Thu. 2/13/97 | Mon. 2/17/97 |
| Enable Monitoring Systems | Thu. 2/13/97 | Mon. 2/17/97 |
| Implement Internet Connection Method | Tue. 2/11/97 | Mon. 2/17/97 |
| Introduce Production Content | Thu. 2/20/97 | Wed. 3/12/97 |
| Develop Conversion Routines/Tools | Thu. 2/20/97 | Wed. 3/5/97 |
| Perform Initial Conversions/Introduce Content | Thu. 3/6/97 | Wed. 3/12/97 |
| Implement Content Management Plan | Mon. 2/17/97 | Mon. 2/24/97 |
| Implement Content Management Tools | Thu. 2/20/97 | Mon. 2/24/97 |
| Implement Content Management Policies and Procedures | Mon. 2/17/97 | Wed. 2/19/97 |
| Implement Security Plan | Thu. 3/6/97 | Wed. 3/19/97 |
| Implement Security Tools | Thu. 3/6/97 | Mon. 3/10/97 |
| Implement Security Policies and Procedures | Mon. 3/17/97 | Wed. 3/19/97 |
| Implement Monitoring Plan | Mon. 3/17/97 | Wed. 3/19/97 |
| Implement Monitoring Tools | Mon. 3/17/97 | Wed. 3/19/97 |
| Implement Monitoring Policies and Procedures | Mon. 3/17/97 | Wed. 3/19/97 |
| Implement Training Plan | Tue. 2/18/97 | Fri. 2/28/97 |
| Secure Vendor Training | Tue. 2/18/97 | Tue. 2/18/97 |
| Conduct Procedural Training | Tue. 2/25/97 | Fri. 2/28/97 |
| Conduct Quality Review | Thu. 3/20/97 | Wed. 3/26/97 |
| Perform Unit Test | Thu. 3/20/97 | Fri. 3/21/97 |
| Perform Alpha Test | Mon. 3/24/97 | Tue. 3/25/97 |
| Perform Principal Review and Sign Off | Wed. 3/26/97 | Wed. 3/26/97 |
| Launch Private Web | Thu. 3/27/97 | Thu. 3/27/97 |
| Implement Internal Promotion Plan | Thu. 3/27/97 | Thu. 3/27/97 |
| Distribute Client Software to Users | Thu. 3/27/97 | Thu. 3/27/97 |
| Announce Availability | Thu. 3/27/97 | Thu. 3/27/97 |

Appendix C – Intranet Development Considerations

Intranet Development Rules

During design and implementation, information gathered from the users and management is used to produce architecture, content and implementation plans for the Intranet project.  The plans produced clearly define and document every aspect of the site design.  Of the thirteen CONSULTANT rules for Intranet development, nine are put to use in designing the Intranet.

Rule 1 - BEGIN WITH THE END IN MIND

It is extremely important to ensure that the driving force behind your prototype application is part of a process that directly produces value for the customer of the organization.  These are typically applications that impact the corporate mission or an identified value stream.  The wish list identifies the available opportunities.  These drivers and other pertinent issues are used to build an Intranet that will generate broad-based support and aid team members in setting goals for the project as a whole.

Rule 2 - MIND THE DETAILS TO ADD ADDITIONAL VALUE

While designing and building applications for the Intranet, note ways that each part of the web can work with other parts in order to create additional value.  Applications can sometimes be improved by taking a business process view of their usage and making improvements.  Sometimes synergy can be achieved between applications that create a great deal of value with very little effort or time.  Once you have a basic structure, the application groupings and the project, as a whole should be reviewed to see where improvements could be made.

Rule 3 - THINK ORGANIZATIONALLY, NOT COMPUTATIONALLY

It is very important to select technologies based on goals and needed functionality, not popularity with other organizations.  When identifying requirements specific functions are identified that are required in order to have a successful system.  This rule warns us to avoid selecting technologies just because “everyone else has it”.  This leads to making decisions based on goals we set considering the specific costs and needs of the organization.

Rule 5 - STAY OFF THE BLEEDING EDGE

Where you really want to be is on the cutting edge, rather than on the bleeding edge.  Stay a little behind the pack and let others discover problems in production.  The Internet is going through a period of rapid discovery where companies will appear on the scene very quickly with new products.  Many will cease to exist in the near future.  Be wary of products and/or companies that are very new and unproven.

Rule 7 - YOU CONTROL THE CHOICE OF TOOLS

In stark contrast to Internet development, Intranet development does not involve developing for any and every hardware and software combination that might be used to reach the site.  Designing for the lowest common denominator in this way narrows the range of possible functions your site can offer.  Since you control the standards and the selection of tools people can use, you can select the tools that offer the functionality your site requirements demand.

Rule 8 - CONTENT IS KING

You need to ensure that your content is compelling and that users can access it in ways that best assist them in doing their jobs.  Ensure that information is accessible when it is needed during a business process and that the Intranet does not do anything to hinder progress.  There are two basic information-sharing metaphors to keep in mind when developing an Intranet:

One is that of a convenience mart, where people can drop in, get what they need and leave,

A second way of looking at the Intranet is to view it as a place somewhere between cybercafe and community library.  A place where people can walk in, hang-out, get to know each other, and get to know more about the company.  Once they have done that, they are more likely to contribute content, rather than just consume what is already there.

The lesson in this is to ensure that the content you provide is something users need and deliver that content in a way that users can easily utilize it.

Rule 10 - LAY YOUR FOUNDATION EARLY

The Intranet serves as a base for future development, both during this project and beyond.  If it can be developed in a way that allows it to be quickly altered to deliver other types of information, then similar information areas can be developed quickly and automatically be consistent with the first area.  This involves two major considerations:

The interface must be one that users accept and find useful within the context of the Intranet as a whole.

The technical design must be flexible, modular, and therefore easy to alter.

Rule 11 - HAVE POLICIES AND PROCEDURES IN PLACE

You must plan for managing information delivery using policies and procedures from the day the Intranet goes live.

Content is delivered from many sources across the organization.  You can have discussion groups, file sharing areas, personal web servers, and other communications vehicles.  In terms of empowering the individual, the impacts of these technologies are tremendous.  However, without proper information management, this can be a problem.  So, develop systems with technology management in mind rather than focusing purely on implementation.

Rule 12 - EAT WHAT YOU COOK

You must have support at all levels for the Intranet.  Getting the involvement of staff through feedback loops, internal marketing, and relationship building is critically important to the success of the project.  Management support is typically gained through developing systems that improve value stream processes.  Grass roots support is many times gained through providing value at lower levels and getting all staff involved in the project.

Rule 13 - PREPARE FOR THE INTRANET TO BECOME MISSION CRITICAL FAST

With the right marketing strategy, your Intranet should be met with a tremendous response from the day it rolls out.  Properly managed from that point on, it will quickly (many times within a month) become a critical part of the way you do business.  This means it must be treated as a production system from the very beginning through a technical maintenance standpoint.  Feedback must be gathered from users and considered in a structured way in order to ensure the continued success and support of the system at all levels of the organization.

Designing the Concept and Visual Architecture

The first step in designing the concept and visual architecture is to create the artistic design and navigational layout for the Intranet site.  This provides an attractive and functional interface for the site and promotes ease of use.  Design parameters are established in order to address the user groups and send the proper message to each user.  Understanding the user groups provides knowledge of what information they will expect or need on the site and how they will use that information.  Important information needed about each group is:

- Number of users in the group?

- How are users related to the group?

- What information are they looking for on the Intranet?

- What processes are they used to dealing with?

- How will they connect to the Intranet?

The Intranet will mean different things to different people.  It is important that the messages sent to each user group are in keeping with the way they view the site.

Do you want the users to view the Intranet as a tool, a place, and a part of the company, a convenience store for information, or a library-style resource?  Given that different groups use information in different ways, the answer may be different for each group or vary within one group based on many factors.  Thinking of metaphors for the way the groups will access the information can provide valuable information for the design process.

Do you want to send a message that says, “This is your site, tell us how to change it”?  Alternatively, do you want to send the message that says, “This is the company’s site, be careful how you use the information we give you”?  Messages like these are important because they affect the users’ perception of the site and affect how they use it.

Depending on their role with the company, some users may stray from the paths you have established for their constituency.  This can be encouraged or discouraged by the design of the site (or the “messages” you send each user).

Navigation design of the site should be based on:

THE CONSTITUENCY ANALYSIS INFORMATION

...Which gives you a feel for the way that each constituency will naturally want to access the site based on the business processes the site supports.

EASE OF NAVIGATION

...And consistency factors.  Ensure that users who stray from their “constituency path” will not be lost on other parts of the site.  Provide a consistent path to important site areas.

THE ACCESS METHOD

...Used by the users needing the information.  Users with slower connections have different requirements than users with fast ones.  They may want to be able to get to what they need within a click or two where users with faster connections may want more options and ability to drill down.

THE TYPE OF INFORMATION

...Needed most.  If 90% of the time, users will only need summary information, having them link to detail rather than downloading all of it at once makes sense.

This task has been intentionally limited by the scope of the Sales Force Automation Intranet.  While the user groups are limited in the initial phase, the final corporate Intranet will need to support user groups from across the company.

Themes and Concepts

A theme and site concept needs to be established for the site.  Themes are the impressions that you want the site to make on the user.  They are consistent with, and should reinforce, the corporate image and culture.

Themes affect the “feel” of the site through:

- Color selection

- Use of language

- Formality of information exchange

- Layout/visual cues.

Themes can be drawn from:

- Company slogans

- Marketing collateral

- Executive speeches

- Shared corporate experiences (things that employees have in common)

- Unique (corporate) cultural attributes

The site concept establishes the Intranet identity.  Something that fits with the corporate image and the way the company is perceived by the world.  A site that has an identity is more likely to draw in users than one that is simply called “<company name> web”.  Components should be designed to fit that concept.

Tying the Visual to the Structural

When the initial visual architecture has been designed, ties must be drawn between the visual and structural architectures.  This allows the designers to understand how the structural design of the site might impact, limit, or enhance the design of page-level interfaces.  Two basic things should be kept in mind:

- How does the overall structure (on-line geometry) affect the visual design of the site?

- How will the data access method affect the look of each interface?

The designers must plan how the on-line Geometry relates to how the information might be displayed on the screen, e.g.,

- Can “color sectioning” be used to denote broad information areas?  In other words, links from the home page to second level areas can be a specific color, reflected in the area itself, and in all subsections of that area.  This gives the user a visual cue as to the part of the site he or she reaches.

- Can frames be used to give context and provide quick access to other areas?  Many times a simple tool bar can be created that will facilitate easy movement through the site.

- Can outline structures be used to facilitate movement through the site?  This is like providing the user with a table of contents or site map on every page.  The user can expand or collapse the outline elements as needed to provide direct access to very low level areas.

The technical designers provide options to allow the appropriate data access to occur.  These options are analyzed to determine what impacts the type of data access required might have on interface design.  Many data access tools will generate the HTML page needed to reach the data.  At times, this page can be modified to suit specific needs.  However, designers should be aware of any limitations the data access method might impose on the design.  In addition, tool-specific features may exist that might enhance the design.

The Home Page

The home page is the front door to the site.  It is where the concept as a whole comes together and users begin their search for information.  All lower-level pages support the concept introduced and promoted on the home page.  It is the most important part of the site from a graphic design standpoint.

The Home page must be laid out so that:

- The site concept is clear and makes it easier for the users to navigate and understand the content on the site.

- The site displays themes that are consistent with the company's beliefs and culture.

- The site is attractive and inviting to users.  It must be technology that they enjoy using.

- The methods used to connect to the site are considered in the design.

- The processes the users are involved in when they are accessing information through this page are considered.

As part of this process, the graphics are created for the site.  The Home page graphics must consider:

- The impact of the graphic on the site concept.  Does the graphic clarify and illustrate the site concept?

- The impact of the graphic on the site themes.  Does the graphic support the themes developed earlier?

- Graphics usage.  Will the graphics themselves be image maps used to access lower level information areas?

- The slowest common connection type used to access the site.  All users will typically start at this page.  If slow-loading graphics are used here, many hours of staff time may be wasted watching images resolve.

- The overall visual appeal of the site.  It must be technology that they enjoy using.

- How the graphics relate to the process.  This refers to the processes users are involved in when they are accessing information through this page.  Do the graphics help to prove visual cues or illustrate a concept?

Quality Assurance

The final step in content design is the Quality Assurance Tests.  These tests ensure that the pages are ready to place into production.  Performing all of these tests before the pages are moved into production will help any problems that crop up during that migration and should include:

- HTML validation.  There are a number of HTML validation tools available on the web.  There may be errant code in the HTML that works well now, but could cause problems to crop up later.

- Link tests.  These are performed to ensure all of the links on your site operate properly.  These tests can be performed one of three ways. 1) Use a link verification tool (packaged with many servers) to view the site and report back broken links.  2) Generate a list of links and have one or more users click through each one.  3) Have users randomly click through the site and report problems.

- Spelling and Grammar checks.  All content should be run through a spell checker and be reviewed by a competent editor.

- Concept Check.  This is subjective, but can be useful.  When your test users are finished with other checks of the site, ask if they understood the concept and metaphors.  Did this help or hinder them?  Ask if the look of the site will work well for the organization and why.

- Usability tests.  Someone considered a "typical user" could perform these.  Give the user a list of items to find with out telling them where to look.  Time them.  Judge the usability of your site by the average speed at which a new user can find information.  You can also make some value judgments by comparing the average hunt times for each item (information type).  The larger your sample the more meaningful the results will be.

- Client Tests.  Try to access the site with every hardware, client and connection combination that users may use in production.

Content Management Plan

The Content Management Plan specifies how to keep content up to date and organized as effectively as possible.  From an information management perspective, it is important to understand how information is created and used within the organization.  Tools must be selected to update and manage content based on the following criteria:

- Who is the gatekeeper?

- What file format is the information in?

- How will actual updates occur?

- Description of the content?

- Who is the owner?

- What is the security method?

- Is there specific handling?

- What is the refresh rate?

Set up one of two content delivery methods:

MANUAL METHOD

Allow developers to have rights to web directories on the server.  This will allow them to move content onto the site over the LAN as they see fit.  If you are developing using this method of file transfer, set up some type of version control scheme on a LAN space that you know will be backed up.

Or

AUTOMATED METHOD

Content delivery using a content management toolset such as Microsoft’s Front Page or Netscape Gold. For this option, you must have certain software extensions installed on their server and establish appropriate rights to the web directories on your server.  This can also provide advanced features, such as version control and dynamic mapping of your site.

Security Management Plan

It is important to understand what physical and software security will be in place and how it protects the information on the Intranet.  Security is always a balancing act.  As long as there are people accessing information and people creating it, no system can be completely secure.  When asked about security, many managers will at first argue for maximum security on all information, since that seems to be the simplest and safest solution to the problem.  However, maximum security comes with both monetary and process-related costs that will many times outweigh its advantages.  When building the security architecture, consider how easily an outsider could access the information under the current system.  Is that information currently stored in a vault or a file cabinet?  Consider how security precautions might limit your users’ access to information they need.

On an Intranet, there are a number of different ways to secure information.  The major security categories are listed two sections below.  The security architecture is documented from two perspectives: how the tools are used and how the information is protected.

BASIC SERVER CONTROLS

- The Intranet server should be used only for Intranet applications.  It should not be used for other purposes.  The server should be kept in a secure room when unattended.

- All interpreters, command shells, daemons, mail servers, applications that are not being used by the Intranet should be removed from the system.

- User accounts (at the server, operating system level) should be kept to a minimum and granted on an as needed basis.

ACCESS CONTROL

- Block access to robots on all pages

- There are three schools of thought on access control.  From safest to least safe they are:

- Block all access and grant rights on an as needed basis.

- Grant limited access to a few areas, but in general grant full access to all users.

- Grant unlimited access to all users.

- Access limitation by user name and password.  This is by far the most popular method of limiting access.

- Access control by IP address.  This limits access to trusted hosts and users by validating IP addresses.

- CGI limitation.  Only administrators should have update access to CGI directories.  Users should not be allowed to create CGI programs that run on the server.

- Server-side includes.  Do not allow users to utilize server-side includes in their programs.  These can have a negative impact on server performance.

TRANSMISSION SECURITY

Data can be intercepted between sender and receiver in one of two ways.  Someone can use a sniffer (a device that can read data packets by being attached to a physical wire) or they can “spoof” (pretend they have) the address of the receiving machine.  One way of preventing this from happening is by encrypting the data before it is sent and decrypting it on the other end.

Ways to use encryption to provide secure transmission include:

- Private Key Encryption.  When systems on both ends of a link use the same method (one key) to scramble and descramble a message.  Examples of this are Data Encryption Standard (DES) and a One-time Pad.

- Public Key Encryption.  Public key algorithms are based on mathematical equations that are easy to work forward, but difficult to work backward.  They use a combination of two keys, a public and a private key, to encrypt and decrypt messages.  An example of this is Pretty Good Privacy (PGP).

- Certificate-based security.  Certificate-based security is based on public key encryption and uses a certifying authority, such as Verisign, Inc. to validate user identity.  In other words, in order to get a certificate, you must go through a certifying process, which at different levels could mean providing identifying information, signing a notarized letter or providing other forms of identification.

- Secure Sockets Layer.  SSL is a public key encryption method and is built into most browsers.  According to Netscape, SSL, “provides data encryption, server authentication, message integrity, and optional client authentication for a TCP/IP connection. “  It is one of the more popular methods for securing your Intranet.

- Secure HTTP (SHTTP).  Again, according to Netscape, “SHTTP is a security-enhanced variant of HTTP proposed by EIT.  SSL and SHTTP have different motivations: SSL layers security beneath application protocols like HTTP, NNTP, and Telnet, whereas SHTTP adds message-based security (drawing on the approaches and philosophies of the PEM and MIME efforts) to HTTP specifically. SSL and SHTTP are not mutually exclusive; rather, they can easily co-exist in a complementary fashion by layering SHTTP on top of SSL.”  In other words, SHTTP is encryption at a different layer from SSL and can be used together to “double-encrypt” messages for added security.

- Hardware-based security.  Keys can also be stored on a hardware device, such as a disk or other attachment that must be used to facilitate communication with a secure site.

The Security Management Plan states the following:

- Description of the content?

- Who is the owner?

- What is the security method?

- Is there specific handling?

- What is the value of access?

- What are the risks if lost?

- What is the chance of loss?

- Whom is it shielded from?

- What is the proposed security?

Monitoring Plan

The Monitoring Plan is used to identify opportunities for improvement in site stability and utilization.  This plan should track usage of pages and server access.

Tracking usage of pages is important, because it will tell you how often pages are being used.  If a page is not being used, you must follow up on that information by finding out why.  Is the content not useful to your audience?   Is it not presented in a useful fashion?  Do users not know it exists?  Having a plan in place will help you to identify unused pages.  Then you can find out why they are not being used and try to correct the situation.

To plan for tracking page accesses, create a weekly (daily or monthly, depending on your needs) schedule for documenting hit counts that include the following:

- Page tracked

- Number of hits

- Date

- Follow-up action taken

- Resolution

Tracking usage of the server will help you to identify periods of variable utilization, aid with capacity planning, and avoid processor overutilization.  Understanding periods of high and low utilization will help you to better plan maintenance schedules.  Knowing if the server is overloaded is important to performance.  Finally, tracking access over time will aid in capacity planning.

To plan for tracking server accesses, create a weekly or monthly schedule for documenting utilization that include the following:

- Hourly server utilization. (up and downs over day-long periods)

- Daily server utilization.  (up and downs over week-long periods)

- Weekly server utilization. (up and downs over month-long periods)

- Monthly server utilization. (up and downs over year-long periods)

Tracking methods and metrics include:

- Number of server connections

- Number of concurrent server connections over time.

- Page counters

- User path tracking

These items can be tracked by:

- Monitoring software packages

- Server logs

- CGI scripts that create logs by USER_ID (as an environment variable)

- Cookies, which carry client-side state information like where a client has visited before, etc.

This plan should also track security events and notify the administrator of important breaches.  Security events can include attempted logins without the proper password, login attempts without proper keys/certificates, corrupted files, unauthorized file alteration, viruses, and other events which may threaten the integrity or privacy of the system.

To plan for tracking security events, create regular schedule for reviewing logs and documenting events that include the following:

- Date

- Time

- Event Type

- Follow-up action taken

- Resolution

The plan should take into account administrator notification, uptime monitoring, and trend analysis, and possible user impacts.

Internal Promotion Plan

An internal promotion is held prior to Intranet deployment in order to gain awareness of, and support at all levels of the organization for the Intranet.

The Internal Promotion Plan objectives should include:

- The constituencies (audiences) being addressed.

- The desired impact on each constituency.

- Goals for usage within a specified time frame.

Sponsors should be chosen in order to establish system champions within the organization.  Each user group should have an assigned sponsor who is responsible for generating interest in Intranet content.

Design promotional activities to generate excitement and promote the Intranet from within the organization.  These activities usually involve system sponsors who take responsibility for generating excitement within specific user groups in support of the new system.

These activities can include:

- Promotional demonstrations

- Marketing campaigns

- Informal discussions/breakout sessions

- Linking system rollout with other positive changes.

Appendix D - Factory Locations

US Factories

Foreign Factories

Contract Facilities