## Slide 1: Normalizing a Project Schedule
Learn how to match resources to tasks within the framework of your schedule.

## Slide 2: For Critical Tasks
Review the project schedule to determine if the resources you assigned are actually available within the schedule window of each task.
After individual assignments are finalized and reviewed by the project team, adjust the schedule to accommodate any other necessary changes.
The schedule must then be reviewed and approved by senior management as part of the project plan.

## Slide 3: For Non-Critical Tasks
Schedule all non-critical tasks at the earliest date possible, thus providing a way to free up resources earlier for other projects or later critical tasks.
Schedule all non-critical tasks as late as possible without causing critical tasks to slip.
Schedule a subset of non-critical tasks.
  As milestones get met, complete the rest of the schedule, thus giving yourself flexibility and a way to assign resources to critical tasks.

## Slide 4: Rules for Assigning Resources
Make sure you know the specific availability of all resources.
Assign the best-suited available people to each task.
Use resources efficiently to ensure the smallest gaps in working schedules.
Redo the schedule until it balances.
If one unique resource commands first place in your project, you must make your schedule conform to its availability. No way around that!