## Introduction
Project Planning and Monitoring Tool
Purpose: This tool assists in organizing and monitoring project work. By using the task planning section, project milestones and tasks can accurately be planned out. Once the project begins, real-time progress is tracked and the project is monitored against the set baselines.
Instructions: This tool can be used for managing a project, starting with the planning stages right through to monitoring project progress. Refer to the boxes below to view each section's instructions, and understand how each step is useful for managing projects. Alternatively, information entered in Microsoft Project can be copied and pasted into this tool to take advantage of its reporting capabilities. A simple copy and paste will work, however there is some preparation needed: 1. Ensure that the fields in MS Project are altered to match this tool. The order should be: Task Name, Start, Finish, and Resource Names. 2. Once pasted into this tool's Tab 2, reformat the start and finish columns to use a date format (within the Format menu, choose "Cells..." and select the desired date format). 3. Resource Names within MS Project must match the naming conventions used in this tool's Tab 1, table 1. Important Notice: Although this tool is capable of advanced functions, keep in mind that this is a light project management tool working within the limitations of Microsoft Excel. Pay close attention to any notices or warnings included within the individual tabs.
Getting Started: In chronological order, use the boxes below to navigate through the tool as the project progresses. Click the blue buttons to go directly to the section of choice, or use the worksheet tabs along the bottom of the spreadsheet screen. Some of the column headings in the sections include comments that offer additional instructions. Hover the mouse over the column headings to view these instructions.
| DATA ENTRY |  | PROJECT TASK PLANNING & MONITORING
| This section requires some basic data entry to get the project started. Information regarding project start and end dates, project team members and stakeholders, and non-work days is required. |  | Use this important section to plan out the project. Tasks should be entered, along with deadlines and task owners. Once hashed out and completed, copy and paste this plan into Tab 3 to begin monitoring project progress.
|  | Go to Data Entry |  | Go to Planning & Monitoring
| ISSUE LOG |  | CUSTOMIZED PROGRESS REPORT
| If issues arise, use this area to log and ensure that problems are resolved. |  | Use this section to generate a custom progress report. Specify the time period that you would like to view and tasks during this time, ordered by task owner, will appear. This report is ideal for weekly meeting updates, or stakeholder progress reporting.
|  | Go to Issue Log |  | Go to Task Report
Info-Tech Research Group tools and template documents are provided for the free and unrestricted use of subscribers to Info-Tech Research Group services. These documents are intended to supply general information only, not specific professional or personal advice, and are not intended to be used as a substitute for any kind of professional advice. Use this document either in whole or in part as a basis and guide for document creation. To customize this document with corporate marks and titles, simply replace the Info-Tech Information in the Header and Footer fields of this document.
3
4
1
2

## 1. Data Entry
Basic Data Entry |  |  | Return to the Introduction
Fill in all of the white cells with the necessary information. To view additional instructions, hover your mouse over the table column headings.
Project Name | CRM Implementation
Estimated Project Start Date | 2009-06-01
Estimated Project End Date | 2009-07-20
Project Manager Name | Jane Doe
1. Project Team Members, Task Groups & Stakeholders | 2. Holidays / Time Off Project
Name | Date | Holiday
Jane Doe | 2009-04-10 | Good Friday
John Doe | 2009-04-13 | Easter Monday
Jane and John | 2009-04-15 | All Day Dept Meeting April
John Smith | 2009-05-18 | Canadian Victoria Day
Kim Lee | 2009-07-04 | US Independence Day
Chris Johnson | 2009-07-03 | Non-Project Work Day
Alex Singh | 2009-10-12 | Canadian Thanksgiving
Marketing Department | 2009-11-26 | US Thanksgiving
Production Team | 2009-12-25 | Christmas Day
| 2010-01-01 | New Year's Day
Note on B14: List all project participants and stakeholders. Include all project member names that will be actually involved with owning/implementing parts of the project. Feel free to insert multiple names of a team.
Note on D14: All dates in this list will not be made available in the project planning gantt chart. Make sure that ranges are printed out one date at a time. For example, if there is a week of non-project work, print out the five days as separate entries. Make sure to include only days that are not dedicated to the project as a whole. Remember, these dates will be blanked out completely.

## 2. Task Monitoring
Work Schedule Monitoring | [11 empty] | Return to the Introduction
IMPORTANT NOTICE: It is very important that the following actions are followed: - Tasks must be entered with unique names. If task names are repeated, the data will not carry over correctly. Name each task differently. - Task Owner must be selected from the drop down menu. If unique names are entered, the report data will not carry over correctly. IMPORTANT NOTICE REGARDING MACROS: Rows can be inserted ONLY by highlighting the desired row or cell and pressing "CTRL i." Rows can be deleted ONLY by highlighting the desired row or cell and pressing "CTRL d." Do not attempt to insert or delete rows through the normal method, as this will result in calculation errors throughout the tool. | [6 empty] | GANTT CHART LEGEND
Holiday / Vacation / No Work
Planned Project Work Day
Task Completed
COMPLETION STATUS LEGEND
Task Completed Ahead of Schedule
Task Completed Behind Schedule
Project Task Information | [6 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26
Project Task | Estimated Start Date | Estimated Completion Date | Task Owner MUST USE DROP DOWN MENU | Actual Start Date | Actual Completion Date | Comments | 2009-06-01 |  |  |  |  | 2009-06-08 |  |  |  |  | 2009-06-15 |  |  |  |  | 2009-06-22 |  |  |  |  | 2009-06-29 |  |  |  |  | 2009-07-06 |  |  |  |  | 2009-07-13 |  |  |  |  | 2009-07-20 |  |  |  |  | 2009-07-27 |  |  |  |  | 2009-08-03 |  |  |  |  | 2009-08-10 |  |  |  |  | 2009-08-17 |  |  |  |  | 2009-08-24 |  |  |  |  | 2009-08-31 |  |  |  |  | 2009-09-07 |  |  |  |  | 2009-09-14 |  |  |  |  | 2009-09-21 |  |  |  |  | 2009-09-28 |  |  |  |  | 2009-10-05 |  |  |  |  | 2009-10-12 |  |  |  |  | 2009-10-19 |  |  |  |  | 2009-10-26 |  |  |  |  | 2009-11-02 |  |  |  |  | 2009-11-09 |  |  |  |  | 2009-11-16 |  |  |  |  | 2009-11-23
[7 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
[31 empty] | H | [70 empty] | H | [32 empty] | H
Project Feasibility Study | 2009-06-01 | 2009-06-03 | John Doe | 2009-06-01 | 2009-06-05 | bar: 2009-06-01 1 M to 2009-06-01 3 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
New Project Sample Task | 2009-06-02 | 2009-06-17 | Kim Lee | 2009-06-03 | bar: 2009-06-01 2 T to 2009-06-15 17 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Cost Benefit Analysis | 2009-06-02 | 2009-06-04 | Jane and John | 2009-06-02 | bar: 2009-06-01 2 T to 2009-06-01 4 T; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Project Definition | 2009-06-06 | 2009-06-08 | Jane Doe | 2009-06-06 | bar: 2009-06-08 8 M; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Assign Resources | 2009-06-08 | 2009-06-09 | John Smith | 2009-06-08 | bar: 2009-06-08 8 M to 2009-06-08 9 T; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Create Project Plan | 2009-06-09 | 2009-06-16 | Kim Lee | bar: 2009-06-08 9 T to 2009-06-15 16 T; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Create Communications Plan | 2009-06-15 | 2009-06-17 | Jane Doe | bar: 2009-06-15 15 M to 2009-06-15 17 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Project Kick-Off Meeting | 2009-06-19 | 2009-06-19 | Jane Doe | bar: 2009-06-15 19 F; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Create Phase 1 Plan and Definition | 2009-06-22 | 2009-06-24 | Jane Doe | bar: 2009-06-22 22 M to 2009-06-22 24 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Phase 1 Execution Kick-Off | 2009-06-24 | 2009-06-24 | Jane Doe | bar: 2009-06-22 24 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Communicate Phase 1 Progress | 2009-06-25 | 2009-07-01 | John Doe | bar: 2009-06-22 25 T to 2009-06-29 1 W; 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Change Control Processes | 2009-07-01 | 2009-07-02 | Jane and John | bar: 2009-06-29 1 W to 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Close Phase 1 | 2009-07-02 | 2009-07-03 | Jane Doe | bar: 2009-06-29 2 T to 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Create Phase 2 Plan and Definition | 2009-07-01 | 2009-07-03 | Chris Johnson | bar: 2009-06-29 1 W to 2009-06-29 3 F; 2009-10-12 12 M; 2009-11-23 26 T
Phase 2 Execution Kick-Off | 2009-07-06 | 2009-07-06 | Chris Johnson | bar: 2009-06-29 3 F to 2009-07-06 6 M; 2009-10-12 12 M; 2009-11-23 26 T
Communicate Phase 2 Progress | 2009-07-07 | 2009-07-09 | Chris Johnson | bar: 2009-06-29 3 F; 2009-07-06 7 T to 2009-07-06 9 T; 2009-10-12 12 M; 2009-11-23 26 T
Change Control Processes | 2009-07-09 | 2009-07-10 | Chris Johnson | bar: 2009-06-29 3 F; 2009-07-06 9 T to 2009-07-06 10 F; 2009-10-12 12 M; 2009-11-23 26 T
Close Phase 2 | 2009-07-13 | 2009-07-14 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 13 M to 2009-07-13 14 T; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
Project Delivery | 2009-07-15 | 2009-07-15 | Production Team | bar: 2009-06-29 3 F; 2009-07-13 15 W; 2009-10-12 12 M; 2009-11-23 26 T
Project Closure Meeting | 2009-07-16 | 2009-07-16 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 16 T; 2009-10-12 12 M; 2009-11-23 26 T
Performance Appraisal | 2009-07-16 | 2009-07-18 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 16 T to 2009-07-13 17 F; 2009-10-12 12 M; 2009-11-23 26 T
Project Feedback Form | 2009-07-16 | 2009-07-18 | Kim Lee | bar: 2009-06-29 3 F; 2009-07-13 16 T to 2009-07-13 17 F; 2009-10-12 12 M; 2009-11-23 26 T
Project Debrief Report | 2009-07-17 | 2009-07-20 | Jane Doe | bar: 2009-06-29 3 F; 2009-07-13 17 F to 2009-07-20 20 M; 2009-10-12 12 M; 2009-11-23 26 T
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
[31 empty] | H | [70 empty] | H | [32 empty] | H
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
Week 12 = [Week 11]+7
Week 13 = [Week 12]+7
Week 14 = [Week 13]+7
Week 15 = [Week 14]+7
Week 16 = [Week 15]+7
Week 17 = [Week 16]+7
Week 18 = [Week 17]+7
Week 19 = [Week 18]+7
Week 20 = [Week 19]+7
Week 21 = [Week 20]+7
Week 22 = [Week 21]+7
Week 23 = [Week 22]+7
Week 24 = [Week 23]+7
Week 25 = [Week 24]+7
Week 26 = [Week 25]+7
Note on B14: The first four columns of this table should be populated by copying and pasting the tasks that were planned out in Tab 2. The only new text that should be entered in this tab is the actual start and end dates.
Note on E14: Use ONLY the drop down menu to select the task owner name. Entering text that is not from the menu will result in reporting errors in Tab 4.
Note on H14: Insert task-specific comments as necessary. If useful, a hyperlink to a specific issue in Tab 4 can be created by hyperlinking within the document.

## 3. Issue Log
Issue Log |  |  | Return to the Introduction
Date | Issue | Comments | Resolution
2009-01-03 | Sample Issue

## 4. Reporting
Customized Progress Report |  |  |  | Return to the Introduction
To create a customized progress report, insert the desired timeframe for analysis in the start and end date boxes below. For a progress report of the entire project, insert the project's start and end dates. Consider running reports based on tasks for today, this week, or next week. IMPORTANT NOTICE: Task owner names must be selected from the drop down menus in Tabs 2 and 3 in order for this reporting page to work correctly. If errors occur on this page, return to the project planning stage and ensure that task owner names were selected from the menus, rather than typed in manually.
Enter Date to Start Progress Report | 2009-06-01 | Enter Date to End Progress Report |  | 2009-07-20
Analysis of On-Schedule Tasks to Date | Analysis of Task Completion to Date |  | Analysis of Project Time Management
Task Owner | Task to be Completed During Specified Period | Task Status | Scheduled Due Date | On Track Status
Jane Doe | Project Definition | Task In Progress | 2009-06-08 | Task is scheduled for work during this timeframe.
| Create Communications Plan | Task Not Yet Started | 2009-06-17 | Task is scheduled for work during this timeframe.
| Project Kick-Off Meeting | Task Not Yet Started | 2009-06-19 | Task is scheduled for work during this timeframe.
| Create Phase 1 Plan and Definition | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
| Phase 1 Execution Kick-Off | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
| Close Phase 1 | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
| Close Phase 2 | Task Not Yet Started | 2009-07-14 | Task is scheduled for work during this timeframe.
| Project Closure Meeting | Task Not Yet Started | 2009-07-16 | Task is scheduled for work during this timeframe.
| Performance Appraisal | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
| Project Debrief Report | Task Not Yet Started | 2009-07-20 | Task is scheduled for work during this timeframe.
Chris Johnson | Create Phase 2 Plan and Definition | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
| Phase 2 Execution Kick-Off | Task Not Yet Started | 2009-07-06 | Task is scheduled for work during this timeframe.
| Communicate Phase 2 Progress | Task Not Yet Started | 2009-07-09 | Task is scheduled for work during this timeframe.
| Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
Kim Lee | New Project Sample Task | Task In Progress | 2009-06-17 | Task is scheduled for work during this timeframe.
| Create Project Plan | Task Not Yet Started | 2009-06-16 | Task is scheduled for work during this timeframe.
| Project Feedback Form | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
Jane and John | Cost Benefit Analysis | Task In Progress | 2009-06-04 | Task is scheduled for work during this timeframe.
| Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
John Doe | Communicate Phase 1 Progress | Task Not Yet Started | 2009-07-01 | Task is scheduled for work during this timeframe.
John Smith | Assign Resources | Task In Progress | 2009-06-09 | Task is scheduled for work during this timeframe.
Production Team | Project Delivery | Task Not Yet Started | 2009-07-15 | Task is scheduled for work during this timeframe.

## Hidden (hidden)
| Variables> | "Stats" |  | Members | Date | Holiday Name
| actual | Not Yet Started | Team--> | Jane Doe | 39913 | Good Friday | Jane Doe
| completion | In Progress |  | John Doe | 39916 | Easter Monday | John Doe
| status | Completed |  | Jane and John | 39918 | All Day Dept Meeting April | Jane and John
|  | Cancelled |  | John Smith | 39951 | Canadian Victoria Day | John Smith
|  |  |  | Kim Lee | 39998 | US Independence Day | Kim Lee
|  |  |  | Chris Johnson | 39997 | Non-Project Work Day | Chris Johnson
|  |  |  | Alex Singh | 40098 | Canadian Thanksgiving | Alex Singh
|  |  |  | Marketing Department | 40143 | US Thanksgiving | Marketing Department
| Status Var> | "Track" |  | Production Team | 40172 | Christmas Day | Production Team
|  | Not Yet Started |  |  | 40179 | New Year's Day
| on track | Completed On Time
| completion | Completed Behind Schedule
| status | Completed Ahead of Schedule
In Progress
Cancelled
LINK PROJECT START DATE TO THE MONDAY BEFORE (For Gantt Chart)
[16 empty] | Which wkday is it? |  |  | Find what day it is | Convert it to Monday
[13 empty] | Start Date | 2009-06-01 |  | Monday |  |  | Sunday
[13 empty] | The Monday | 2009-06-01 |  | Monday |  |  | Monday | 39965
Tuesday
Wednesday
Thursday
Friday
Saturday
#For Tab 5 - Schedule Plan
#NO WORK HOLIDAY DATES
Week of | 2009-06-01 |  |  |  |  | 2009-06-08 |  |  |  |  | 2009-06-15 |  |  |  |  | 2009-06-22 |  |  |  |  | 2009-06-29 |  |  |  |  | 2009-07-06 |  |  |  |  | 2009-07-13 |  |  |  |  | 2009-07-20 |  |  |  |  | 2009-07-27 |  |  |  |  | 2009-08-03 |  |  |  |  | 2009-08-10 |  |  |  |  | 2009-08-17 |  |  |  |  | 2009-08-24 |  |  |  |  | 2009-08-31 |  |  |  |  | 2009-09-07 |  |  |  |  | 2009-09-14 |  |  |  |  | 2009-09-21 |  |  |  |  | 2009-09-28 |  |  |  |  | 2009-10-05 |  |  |  |  | 2009-10-12 |  |  |  |  | 2009-10-19 |  |  |  |  | 2009-10-26 |  |  |  |  | 2009-11-02 |  |  |  |  | 2009-11-09 |  |  |  |  | 2009-11-16 |  |  |  |  | 2009-11-23
Day Date | 39965 | 39966 | 39967 | 39968 | 39969 | 39972 | 39973 | 39974 | 39975 | 39976 | 39979 | 39980 | 39981 | 39982 | 39983 | 39986 | 39987 | 39988 | 39989 | 39990 | 39993 | 39994 | 39995 | 39996 | 39997 | 40000 | 40001 | 40002 | 40003 | 40004 | 40007 | 40008 | 40009 | 40010 | 40011 | 40014 | 40015 | 40016 | 40017 | 40018 | 40021 | 40022 | 40023 | 40024 | 40025 | 40028 | 40029 | 40030 | 40031 | 40032 | 40035 | 40036 | 40037 | 40038 | 40039 | 40042 | 40043 | 40044 | 40045 | 40046 | 40049 | 40050 | 40051 | 40052 | 40053 | 40056 | 40057 | 40058 | 40059 | 40060 | 40063 | 40064 | 40065 | 40066 | 40067 | 40070 | 40071 | 40072 | 40073 | 40074 | 40077 | 40078 | 40079 | 40080 | 40081 | 40084 | 40085 | 40086 | 40087 | 40088 | 40091 | 40092 | 40093 | 40094 | 40095 | 40098 | 40099 | 40100 | 40101 | 40102 | 40105 | 40106 | 40107 | 40108 | 40109 | 40112 | 40113 | 40114 | 40115 | 40116 | 40119 | 40120 | 40121 | 40122 | 40123 | 40126 | 40127 | 40128 | 40129 | 40130 | 40133 | 40134 | 40135 | 40136 | 40137 | 40140 | 40141 | 40142 | 40143 | 40144
HOLIDAY? | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No
39913
39916
39918
39951
39998
39997 | [24 empty] | X
40098 | [95 empty] | X
40143 | [128 empty] | X
40172
40179
[8 empty] | For Pie chart 2 in Today's View - TOTAL PROJECT |  |  |  | For Pie chart 1 in Today - Today's Tasks |  |  |  | For Time Line in Today |  |  | Not subtracting weekends & holidays… | [6 empty] | Task is underway but is behind schedule.
|  |  |  | Today | 2026-07-31 | CODE TASKS FOR THIS WEEK…. Ugh/ |  | Tasks Completed | 4.348% |  |  | Behind Schedule Tasks - Started | 0 |  |  | Project Start | 39965 |  | Project Days Passed | 6269 | 12794% |  |  |  |  | Task is late and has not yet been started.
[8 empty] | Tasks In Progress | 17.39% |  |  | Behind Schedule Tasks - Not Yet Started | 0 |  |  | Today | 46234 |  | Project Days Left | -6220 | -12694%
|  | AMOUNT | of valid tasks |  |  |  |  | Tasks Not Yet Started | 78.26% |  |  | Regularly Scheduled Tasks | 1 |  |  | Project End | 40014
|  | 22 |  |  | Total tasks | 23 | [5 empty] | QC | 1 | [5 empty] | QC | 49
[8 empty] | QC | 100% | [10 empty] | 49
Note on N30: From user input
Note on N31: The Monday of the first week of project commencement...

## HiddenWkly (hidden)
"Weekly" (or whatever) task view | [10 empty] | Task Not Yet Started |  |  | Task is underway but is behind schedule.
[11 empty] | Task Complete |  |  | Task is late and has not yet been started.
start date entry | 2009-06-01 | [9 empty] | Task In Progress |  |  | Task is scheduled for work during this timeframe.
End date entry | 2009-07-20
[26 empty] | TO ORDER BY TASK OWNER |  |  |  |  | Actual list for Tab
TASK NUMBER | ID for Task | "Rank" to list | Repeat Task for VLOOKUP | TASK | Estimated Start Date | Estimated End Date | Owner | Owner for List | Actual Start Date | Actual End Date |  | On Track Status | Task should be done - Started | Task Should be done - Not Yet Started | Reg Scheduled Task during this time | Sum | Unique Rank for Owners, by task | Owner Rank | Task Owner | List of tasks | Task Name | Est Start Date | Est End Date - DUE DATE | Completion Status | On Track Status | Possible Owner | Task Number | Yes to tasks | Unique Rank |  | RANK | Owner | Owner for Tab | Task | Task Status | Due Date | Completion Status
1 | [14 empty] | No | 1 | 15 | 3 | Kim Lee | 1 | New Project Sample Task | 39966 | 39981 | Task In Progress | Task is scheduled for work during this timeframe. | Unassigned | 0 |  |  | Jane Doe | 1 | Jane Doe | Jane Doe | Project Definition | Task In Progress | 2009-06-08 | Task is scheduled for work during this timeframe.
2 |  |  |  | Project Feasibility Study | 39965 | 39967 | John Doe | John Doe | 2009-06-01 | 2009-06-05 | Task Complete |  | No | No | No | 3 | 18 | 4 | Jane and John | 2 | Cost Benefit Analysis | 39966 | 39968 | Task In Progress | Task is scheduled for work during this timeframe. | Jane Doe | 10 | 10 | 1 | John Doe | 2 | Jane Doe |  | Create Communications Plan | Task Not Yet Started | 2009-06-17 | Task is scheduled for work during this timeframe.
3 | 3 | 1 | New Project Sample Task | New Project Sample Task | 39966 | 39981 | Kim Lee | Kim Lee | 2009-06-03 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 6 | 1 | 1 | Jane Doe | 3 | Project Definition | 39970 | 39972 | Task In Progress | Task is scheduled for work during this timeframe. | John Doe | 1 | 1 | 5 | Jane and John | 3 | Jane Doe |  | Project Kick-Off Meeting | Task Not Yet Started | 2009-06-19 | Task is scheduled for work during this timeframe.
4 | 4 | 2 | Cost Benefit Analysis | Cost Benefit Analysis | 39966 | 39968 | Jane and John | Jane and John | 2009-06-02 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 10 | 21 | 6 | John Smith | 4 | Assign Resources | 39972 | 39973 | Task In Progress | Task is scheduled for work during this timeframe. | Jane and John | 2 | 2 | 4 | John Smith | 4 | Jane Doe |  | Create Phase 1 Plan and Definition | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
5 | [14 empty] | No | 15 | 16 | 3 | Kim Lee | 5 | Create Project Plan | 39973 | 39980 | Task Not Yet Started | Task is scheduled for work during this timeframe. | John Smith | 1 | 1 | 6 | Kim Lee | 5 | Jane Doe |  | Phase 1 Execution Kick-Off | Task Not Yet Started | 2009-06-24 | Task is scheduled for work during this timeframe.
6 | 6 | 3 | Project Definition | Project Definition | 39970 | 39972 | Jane Doe | Jane Doe | 2009-06-06 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 21 | 2 | 1 | Jane Doe | 6 | Create Communications Plan | 39979 | 39981 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Kim Lee | 3 | 3 | 3 | Chris Johnson | 6 | Jane Doe |  | Close Phase 1 | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
7 | 7 | 4 | Assign Resources | Assign Resources | 39972 | 39973 | John Smith | John Smith | 2009-06-08 |  | Task In Progress | Task is scheduled for work during this timeframe. | No | No | Yes | 28 | 3 | 1 | Jane Doe | 7 | Project Kick-Off Meeting | 39983 | 39983 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Chris Johnson | 4 | 4 | 2 | Alex Singh | 7 | Jane Doe |  | Close Phase 2 | Task Not Yet Started | 2009-07-14 | Task is scheduled for work during this timeframe.
8 | [14 empty] | No | 36 | 4 | 1 | Jane Doe | 8 | Create Phase 1 Plan and Definition | 39986 | 39988 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Alex Singh | 0 |  |  | Marketing Department | 8 | Jane Doe |  | Project Closure Meeting | Task Not Yet Started | 2009-07-16 | Task is scheduled for work during this timeframe.
9 | 9 | 5 | Create Project Plan | Create Project Plan | 39973 | 39980 | Kim Lee | Kim Lee |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 45 | 5 | 1 | Jane Doe | 9 | Phase 1 Execution Kick-Off | 39988 | 39988 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Marketing Department | 0 |  |  | Production Team | 9 | Jane Doe |  | Performance Appraisal | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
10 | 10 | 6 | Create Communications Plan | Create Communications Plan | 39979 | 39981 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 55 | 20 | 5 | John Doe | 10 | Communicate Phase 1 Progress | 39989 | 39995 | Task Not Yet Started | Task is scheduled for work during this timeframe. | Production Team | 1 | 1 | 7 | 0 | 10 | Jane Doe |  | Project Debrief Report | Task Not Yet Started | 2009-07-20 | Task is scheduled for work during this timeframe.
11 | 11 | 7 | Project Kick-Off Meeting | Project Kick-Off Meeting | 39983 | 39983 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 66 | 19 | 4 | Jane and John | 11 | Change Control Processes | 39995 | 39996 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 11 | Chris Johnson | Chris Johnson | Create Phase 2 Plan and Definition | Task Not Yet Started | 2009-07-03 | Task is scheduled for work during this timeframe.
12 | 12 | 8 | Create Phase 1 Plan and Definition | Create Phase 1 Plan and Definition | 39986 | 39988 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 78 | 6 | 1 | Jane Doe | 12 | Close Phase 1 | 39996 | 39997 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 12 | Chris Johnson |  | Phase 2 Execution Kick-Off | Task Not Yet Started | 2009-07-06 | Task is scheduled for work during this timeframe.
13 | 13 | 9 | Phase 1 Execution Kick-Off | Phase 1 Execution Kick-Off | 39988 | 39988 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 91 | 11 | 2 | Chris Johnson | 13 | Create Phase 2 Plan and Definition | 39995 | 39997 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 13 | Chris Johnson |  | Communicate Phase 2 Progress | Task Not Yet Started | 2009-07-09 | Task is scheduled for work during this timeframe.
14 | 14 | 10 | Communicate Phase 1 Progress | Communicate Phase 1 Progress | 39989 | 39995 | John Doe | John Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 105 | 12 | 2 | Chris Johnson | 14 | Phase 2 Execution Kick-Off | 40000 | 40000 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 14 | Chris Johnson |  | Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
15 | [14 empty] | No | 120 | 13 | 2 | Chris Johnson | 15 | Communicate Phase 2 Progress | 40001 | 40003 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 15 | Kim Lee | Kim Lee | New Project Sample Task | Task In Progress | 2009-06-17 | Task is scheduled for work during this timeframe.
16 | 16 | 11 | Change Control Processes | Change Control Processes | 39995 | 39996 | Jane and John | Jane and John |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 136 | 14 | 2 | Chris Johnson | 16 | Change Control Processes | 39995 | 39996 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 16 | Kim Lee |  | Create Project Plan | Task Not Yet Started | 2009-06-16 | Task is scheduled for work during this timeframe.
17 | 17 | 12 | Close Phase 1 | Close Phase 1 | 39996 | 39997 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 153 | 7 | 1 | Jane Doe | 17 | Close Phase 2 | 40007 | 40008 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 17 | Kim Lee |  | Project Feedback Form | Task Not Yet Started | 2009-07-18 | Task is scheduled for work during this timeframe.
18 | [14 empty] | No | 171 | 22 | 7 | Production Team | 18 | Project Delivery | 40009 | 40009 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 18 | Jane and John | Jane and John | Cost Benefit Analysis | Task In Progress | 2009-06-04 | Task is scheduled for work during this timeframe.
19 | 19 | 13 | Create Phase 2 Plan and Definition | Create Phase 2 Plan and Definition | 39995 | 39997 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 190 | 8 | 1 | Jane Doe | 19 | Project Closure Meeting | 40010 | 40010 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 19 | Jane and John |  | Change Control Processes | Task Not Yet Started | 2009-07-02 | Task is scheduled for work during this timeframe.
20 | 20 | 14 | Phase 2 Execution Kick-Off | Phase 2 Execution Kick-Off | 40000 | 40000 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 210 | 9 | 1 | Jane Doe | 20 | Performance Appraisal | 40010 | 40012 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 20 | John Doe | John Doe | Communicate Phase 1 Progress | Task Not Yet Started | 2009-07-01 | Task is scheduled for work during this timeframe.
21 | 21 | 15 | Communicate Phase 2 Progress | Communicate Phase 2 Progress | 40001 | 40003 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 231 | 17 | 3 | Kim Lee | 21 | Project Feedback Form | 40010 | 40012 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 21 | John Smith | John Smith | Assign Resources | Task In Progress | 2009-06-09 | Task is scheduled for work during this timeframe.
22 | 22 | 16 | Change Control Processes | Change Control Processes | 40003 | 40004 | Chris Johnson | Chris Johnson |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 253 | 10 | 1 | Jane Doe | 22 | Project Debrief Report | 40011 | 40014 | Task Not Yet Started | Task is scheduled for work during this timeframe. | 0 |  |  |  | 0 | 22 | Production Team | Production Team | Project Delivery | Task Not Yet Started | 2009-07-15 | Task is scheduled for work during this timeframe.
23 | 23 | 17 | Close Phase 2 | Close Phase 2 | 40007 | 40008 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 276 | [9 empty] | 0 |  |  |  | 0 | 23
24 | [14 empty] | No | 300 | [9 empty] | 0 |  |  |  | 0 | 24
25 | 25 | 18 | Project Delivery | Project Delivery | 40009 | 40009 | Production Team | Production Team |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 325 | [9 empty] | 0 |  |  |  | 0 | 25
26 | 26 | 19 | Project Closure Meeting | Project Closure Meeting | 40010 | 40010 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 351 | [9 empty] | 0 |  |  |  | 0 | 26
27 | 27 | 20 | Performance Appraisal | Performance Appraisal | 40010 | 40012 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 378 | [9 empty] | 0 |  |  |  | 0 | 27
28 | 28 | 21 | Project Feedback Form | Project Feedback Form | 40010 | 40012 | Kim Lee | Kim Lee |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 406 | [9 empty] | 0 |  |  |  | 0 | 28
29 | 29 | 22 | Project Debrief Report | Project Debrief Report | 40011 | 40014 | Jane Doe | Jane Doe |  |  | Task Not Yet Started | Task is scheduled for work during this timeframe. | No | No | Yes | 435 | [9 empty] | 0 |  |  |  | 0 | 29
30 | [14 empty] | No | 465 | [9 empty] | 0 |  |  |  | 0 | 30
31 | [14 empty] | No | 496 | [9 empty] | 0 |  |  |  | 0 | 31
32 | [14 empty] | No | 528 | [9 empty] | 0 |  |  |  | 0 | 32
33 | [14 empty] | No | 561 | [9 empty] | 0 |  |  |  | 0 | 33
34 | [14 empty] | No | 595 | [9 empty] | 0 |  |  |  | 0 | 34
35 | [14 empty] | No | 630 | [9 empty] | 0 |  |  |  | 0 | 35
36 | [14 empty] | No | 666 | [9 empty] | 0 |  |  |  | 0 | 36
37 | [14 empty] | No | 703 | [9 empty] | 0 |  |  |  | 0 | 37
38 | [14 empty] | No | 741 | [9 empty] | 0 |  |  |  | 0 | 38
39 | [14 empty] | No | 780 | [9 empty] | 0 |  |  |  | 0 | 39
40 | [14 empty] | No | 820 | [9 empty] | 0 |  |  |  | 0 | 40
41 | [14 empty] | No | 861 | [9 empty] | 0 |  |  |  | 0 | 41
42 | [14 empty] | No | 903 | [14 empty] | 42
43 | [14 empty] | No | 946 | [14 empty] | 43
44 | [14 empty] | No | 990 | [14 empty] | 44
45 | [14 empty] | No | 1035 | [14 empty] | 45
46 | [14 empty] | No | 1081 | [14 empty] | 46
47 | [14 empty] | No | 1128 | [14 empty] | 47
48 | [14 empty] | No | 1176 | [14 empty] | 48
49 | [14 empty] | No | 1225 | [14 empty] | 49
50 | [14 empty] | No | 1275 | [14 empty] | 50
51 | [14 empty] | No | 1326 | [14 empty] | 51
52 | [14 empty] | No | 1378 | [14 empty] | 52
53 | [14 empty] | No | 1431 | [14 empty] | 53
54 | [14 empty] | No | 1485 | [14 empty] | 54
55 | [14 empty] | No | 1540 | [14 empty] | 55
56 | [14 empty] | No | 1596 | [14 empty] | 56
57 | [14 empty] | No | 1653 | [14 empty] | 57
58 | [14 empty] | No | 1711 | [14 empty] | 58
59 | [14 empty] | No | 1770 | [14 empty] | 59
60 | [14 empty] | No | 1830 | [14 empty] | 60
61 | [14 empty] | No | 1891 | [14 empty] | 61
62 | [14 empty] | No | 1953 | [14 empty] | 62
63 | [14 empty] | No | 2016 | [14 empty] | 63
64 | [14 empty] | No | 2080 | [14 empty] | 64
65 | [14 empty] | No | 2145 | [14 empty] | 65
66 | [14 empty] | No | 2211 | [14 empty] | 66
67 | [14 empty] | No | 2278 | [14 empty] | 67
68 | [14 empty] | No | 2346 | [14 empty] | 68
69 | [14 empty] | No | 2415 | [14 empty] | 69
70 | [14 empty] | No | 2485 | [14 empty] | 70
71 | [14 empty] | No | 2556 | [14 empty] | 71
72 | [14 empty] | No | 2628 | [14 empty] | 72
73 | [14 empty] | No | 2701 | [14 empty] | 73
74 | [14 empty] | No | 2775 | [14 empty] | 74
75 | [14 empty] | No | 2850 | [14 empty] | 75
76 | [14 empty] | No | 2926 | [14 empty] | 76
77 | [14 empty] | No | 3003 | [14 empty] | 77
78 | [14 empty] | No | 3081 | [14 empty] | 78
79 | [14 empty] | No | 3160 | [14 empty] | 79
80 | [14 empty] | No | 3240 | [14 empty] | 80
81 | [14 empty] | No | 3321 | [14 empty] | 81
82 | [14 empty] | No | 3403 | [14 empty] | 82
83 | [14 empty] | No | 3486 | [14 empty] | 83
84 | [14 empty] | No | 3570 | [14 empty] | 84
85 | [14 empty] | No | 3655 | [14 empty] | 85
86 | [14 empty] | No | 3741 | [14 empty] | 86
87 | [14 empty] | No | 3828 | [14 empty] | 87
88 | [14 empty] | No | 3916 | [14 empty] | 88
89 | [14 empty] | No | 4005 | [14 empty] | 89
90 | [14 empty] | No | 4095 | [14 empty] | 90
91 | [14 empty] | No | 4186 | [14 empty] | 91
92 | [14 empty] | No | 4278 | [14 empty] | 92
93 | [14 empty] | No | 4371 | [14 empty] | 93
94 | [14 empty] | No | 4465 | [14 empty] | 94
95 | [14 empty] | No | 4560 | [14 empty] | 95
96 | [14 empty] | No | 4656 | [14 empty] | 96
97 | [14 empty] | No | 4753 | [14 empty] | 97
98 | [14 empty] | No | 4851 | [14 empty] | 98
99 | [14 empty] | No | 4950 | [14 empty] | 99
100 | [14 empty] | No | 5050 | [14 empty] | 100
101 | [14 empty] | No | 5151
102 | [14 empty] | No | 5253
103 | [14 empty] | No | 5356
104 | [14 empty] | No | 5460
105 | [14 empty] | No | 5565
106 | [14 empty] | No | 5671
107 | [14 empty] | No | 5778
108 | [14 empty] | No | 5886
109 | [14 empty] | No | 5995
110 | [14 empty] | No | 6105
111 | [14 empty] | No | 6216
112 | [14 empty] | No | 6328
113 | [14 empty] | No | 6441
114 | [14 empty] | No | 6555
115 | [14 empty] | No | 6670
116 | [14 empty] | No | 6786
117 | [14 empty] | No | 6903
118 | [14 empty] | No | 7021
119 | [14 empty] | No | 7140
120 | [14 empty] | No | 7260
121 | [14 empty] | No | 7381
122 | [14 empty] | No | 7503
123 | [14 empty] | No | 7626
124 | [14 empty] | No | 7750
125 | [14 empty] | No | 7875
126 | [14 empty] | No | 8001
127 | [14 empty] | No | 8128
128 | [14 empty] | No | 8256
129 | [14 empty] | No | 8385
130 | [14 empty] | No | 8515
131 | [14 empty] | No | 8646
132 | [14 empty] | No | 8778
133 | [14 empty] | No | 8911
134 | [14 empty] | No | 9045
135 | [14 empty] | No | 9180
136 | [14 empty] | No | 9316
137 | [14 empty] | No | 9453
138 | [14 empty] | No | 9591
139 | [14 empty] | No | 9730
140 | [14 empty] | No | 9870
141 | [14 empty] | No | 10011
142 | [14 empty] | No | 10153
143 | [14 empty] | No | 10296
144 | [14 empty] | No | 10440
145 | [14 empty] | No | 10585
146 | [14 empty] | No | 10731
147 | [14 empty] | No | 10878
148 | [14 empty] | No | 11026
149 | [14 empty] | No | 11175
150 | [14 empty] | No | 11325
151 | [14 empty] | No | 11476
152 | [14 empty] | No | 11628
153 | [14 empty] | No | 11781
154 | [14 empty] | No | 11935
155 | [14 empty] | No | 12090
156 | [14 empty] | No | 12246
157 | [14 empty] | No | 12403
158 | [14 empty] | No | 12561
159 | [14 empty] | No | 12720
160 | [14 empty] | No | 12880
161 | [14 empty] | No | 13041
162 | [14 empty] | No | 13203
163 | [14 empty] | No | 13366
164 | [14 empty] | No | 13530
165 | [14 empty] | No | 13695
166 | [14 empty] | No | 13861
167 | [14 empty] | No | 14028
168 | [14 empty] | No | 14196
169 | [14 empty] | No | 14365
170 | [14 empty] | No | 14535
171 | [14 empty] | No | 14706
172 | [14 empty] | No | 14878
173 | [14 empty] | No | 15051
174 | [14 empty] | No | 15225
175 | [14 empty] | No | 15400
176 | [14 empty] | No | 15576
177 | [14 empty] | No | 15753
178 | [14 empty] | No | 15931
179 | [14 empty] | No | 16110
180 | [14 empty] | No | 16290
181 | [14 empty] | No | 16471
182 | [14 empty] | No | 16653
183 | [14 empty] | No | 16836
184 | [14 empty] | No | 17020
185 | [14 empty] | No | 17205
186 | [14 empty] | No | 17391
187 | [14 empty] | No | 17578
188 | [14 empty] | No | 17766
189 | [14 empty] | No | 17955
190 | [14 empty] | No | 18145
191 | [14 empty] | No | 18336
192 | [14 empty] | No | 18528
193 | [14 empty] | No | 18721
194 | [14 empty] | No | 18915
195 | [14 empty] | No | 19110
196 | [14 empty] | No | 19306
197 | [14 empty] | No | 19503
198 | [14 empty] | No | 19701
199 | [14 empty] | No | 19900
200 | [14 empty] | No | 20100
201 | [14 empty] | No | 20301
202 | [14 empty] | No | 20503
203 | [14 empty] | No | 20706
204 | [14 empty] | No | 20910
205 | [14 empty] | No | 21115
206 | [14 empty] | No | 21321
207 | [14 empty] | No | 21528
208 | [14 empty] | No | 21736
209 | [14 empty] | No | 21945
210 | [14 empty] | No | 22155
211 | [14 empty] | No | 22366
212 | [14 empty] | No | 22578
213 | [14 empty] | No | 22791
214 | [14 empty] | No | 23005
215 | [14 empty] | No | 23220
216 | [14 empty] | No | 23436
217 | [14 empty] | No | 23653
218 | [14 empty] | No | 23871
219 | [14 empty] | No | 24090
220 | [14 empty] | No | 24310
221 | [14 empty] | No | 24531
222 | [14 empty] | No | 24753
223 | [14 empty] | No | 24976
224 | [14 empty] | No | 25200
225 | [14 empty] | No | 25425
226 | [14 empty] | No | 25651
227 | [14 empty] | No | 25878
228 | [14 empty] | No | 26106
229 | [14 empty] | No | 26335
230 | [14 empty] | No | 26565
231 | [14 empty] | No | 26796
232 | [14 empty] | No | 27028
233 | [14 empty] | No | 27261
234 | [14 empty] | No | 27495
235 | [14 empty] | No | 27730
236 | [14 empty] | No | 27966
237 | [14 empty] | No | 28203
238 | [14 empty] | No | 28441
239 | [14 empty] | No | 28680
240 | [14 empty] | No | 28920
241 | [14 empty] | No | 29161
242 | [14 empty] | No | 29403
243 | [14 empty] | No | 29646
244 | [14 empty] | No | 29890
245 | [14 empty] | No | 30135
246 | [14 empty] | No | 30381
247 | [14 empty] | No | 30628
248 | [14 empty] | No | 30876
249 | [14 empty] | No | 31125
250 | [14 empty] | No | 31375
251 | [14 empty] | No | 31626
252 | [14 empty] | No | 31878
253 | [14 empty] | No | 32131
254 | [14 empty] | No | 32385
255 | [14 empty] | No | 32640
256 | [14 empty] | No | 32896
257 | [14 empty] | No | 33153
258 | [14 empty] | No | 33411
259 | [14 empty] | No | 33670
260 | [14 empty] | No | 33930
261 | [14 empty] | No | 34191
262 | [14 empty] | No | 34453
263 | [14 empty] | No | 34716
264 | [14 empty] | No | 34980
265 | [14 empty] | No | 35245
[15 empty] | No | 35245
Formulas:
Due Date = IF(SUM(S10:S109)<[Sum],"",VLOOKUP([RANK],S10:AA109,7,FALSE()))