## 1-Instructions
Use the section below to keep track of basic information about your project, and monitor your project stakeholders. You likely won't expect this information to change very often, but it easily can. Come back to check this page at least once a week. Keep an eye out for red areas in particular.
[6 empty] | PROJECT STAKEHOLDERS | [5 empty] | If any stakeholders are not available when input is required, there is a risk that work may either stall or have to be redone. If the answer to the question below is "Yes", a red flag will be raised on the dashboard.
| REPORT DATE: |  | 2010-01-03 |  |  | Stakeholders are people who have a "stake" or interest in your project. It's important to keep tabs on your stakeholders at all times because they may block or alter your project in ways that can keep you from getting to end of job. Also, keep looking out for new stakeholders because a latecomer can have serious impacts to your project.
| Project Name: |  | [Enter your project's name] |  |  | Name | Position in the Company | What is their primary interest in this project? | Has this stakeholder been newly identified? (Answer "No" if this is the first report) | Is this stakeholder's input required during the next reporting period? | Will this stakeholder be available during the next reporting period?
| Project Number: |  | [Enter the number for your project]
| Project Sponsor: |  | [Enter your project sponsor's name]
| Project Manager: |  | [Enter your project manager's name]
[6 empty] | Sample stakeholder 1 | Senior Vice President | Cost containment | NO | NO | NO
[6 empty] | Sample stakeholder 2 | Vice President | Company reputation | NO | NO | NO | Will stakeholder availability be a problem during the next reporting period? | YES
[6 empty] | Sample stakeholder 3 | Legal Counsel | Company exposure to litigation | NO | YES | YES
| Project Baseline: |  | Baseline Cost | Cost Check |  | Sample stakeholder 4 | Marketing | Proper use of branding | NO | NO | NO
|  |  | 25000 | 28780 | No Match | Sample stakeholder 5 | Information Technology | Use of resources | NO | NO | YES
|  |  | Enter the Baseline Cost. Remember to change the baseline cost each time a change request is approved. | The baseline cost should reconcile with the sum of the baseline costs on tab 4-Cost.
If any stakeholders have been newly identified, there is a risk they may block work in progress. If the answer to the question below is "Yes", a yellow flag will be raised on the dashboard.
[12 empty] | Have any stakeholders been newly identified? | NO
Is there doubt about this objective?
| Project Objectives: | [10 empty] | Be prepared to discuss the details if the answer to either of the questions above is "YES".
| #1 | [Enter your top project objective] |  |  | YES
| #2 | [Enter a second project objective] |  |  | NO
| #3 | [Enter a third project objective] |  |  | NO
If there is doubt about a particular objective, the scope of the project is in danger. A "Yes" to doubt above will raise a yellow flag on the dashboard.
It's Easy. It provides novice project managers with a guide to tracking the different moving parts of their projects.
1
It Lets You Communicate. More people are familiar with Microsoft Excel than are with Microsoft Project or more intricate portfolio management tools.
2
It Lets You Preview. Updating project plans can be time consuming if you make a mistake.
3
It Contains No Macros. You won't get any annoying pop up warnings from the original file (if you do get macro pop ups the file has been tampered with).
4
It's Flexible. As a workbook, it was designed to let you perform routine Excel functions like sort and filter without "breaking" any formulas.
5
A WORD OF CAUTION: You are free to modify any part of this book, but advanced knowledge of Microsoft Excel is highly recommended before doing so. Be advised that Microsoft Excel is not a robust project planning tool, and does not take the place of expertise or other tools specifically designed to manage projects. Excel is still a spreadsheet application and should not be considered as a formal tracking tool for medium to large projects.
Grey cells contain formulas and should never be deleted.
Fill formulas down as you need more. This workbook is unprotected for your convenience, but you may protect it so you don't accidentally delete formulas.
Red text cells are areas of the workbook you should check and maintain before every status report. They are key to good project housekeeping.
Pink text contains instructions on how to use the sheet, or special notes about the nearby cells.
This workbook contains 10 tabs that monitor different aspects of your project. Each page links to other pages, filling in more details for you, as you get more information. Work through each tab in the order they are presented. At the end of the workbook is a dashboard you can use for management reporting that provides a graphical display of all aspects of your project that are kept in this book.

## 2-Milestones
Num | Milestone | Percent Complete (Fill Down) | Originally Planned Start Date (dd-mmm-yyyy) | Originally Planned Completion Date (dd-mmm-yyyy) | Actual Start Date (dd-mmm-yyyy) | Actual or Expected Completion Date (dd-mmm-yyyy) | Baseline Duration | Revised Duration | Start Variance (Days) | End Variance (Days)
1 | First Phase Complete | 100% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Second Phase Complete | 37.5% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Third Phase Complete | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | Fourth Phase Complete | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 |  | 0% | - | - | - | - | - | - | 0 | 0
6 |  | 0% | - | - | - | - | - | - | 0 | 0
7 |  | 0% | - | - | - | - | - | - | 0 | 0
8 |  | 0% | - | - | - | - | - | - | 0 | 0
9 |  | 0% | - | - | - | - | - | - | 0 | 0
10 |  | 0% | - | - | - | - | - | - | 0 | 0
11 |  | 0% | - | - | - | - | - | - | 0 | 0
12 |  | 0% | - | - | - | - | - | - | 0 | 0
13 |  | 0% | - | - | - | - | - | - | 0 | 0
14 |  | 0% | - | - | - | - | - | - | 0 | 0
15 |  | 0% | - | - | - | - | - | - | 0 | 0
Milestones are important events on a project that usually mark the completion of a large portion of work. Tasks lead up to milestones, so how close a milestone is to completion depends on what percent of the preceding tasks are done. Use this worksheet to keep track of all your project milestones.
Important: The Milestones you set on this tab are used on tab 3-Tasks and 5-Costs. Be careful that you don't rename your milestones once you've started adding in tasks. If you do, you'll need to check tabs 3-Tasks and 5-Costs to ensure changes are reflected there.
Important: If you raise any change requests, add any milestones you had to go back and change as NEW milestones with the word "change". This will ensure you keep work you already completed separate from work you have to redo.

## 3-Tasks
Num | Project Task | Which of your Milestones Does This Task Work Towards? | Baseline Start Date | Baseline End Date | Actual or Revised Start Date | Actual or Revised End Date | Suggested Revised Start Date | Suggested Revised End Date | Baseline Duration | Revised Duration | Percent of Task Complete | Baseline Cost | Actual Cost Spent to Date | Current Estimate to Complete | Total Task Cost | Variance from Baseline in Dollars | Variance from Baseline in Percent
1 | Sample Task 1 | First Phase Complete | 2009-09-15 | 2009-09-25 | 2009-09-20 | 2009-09-23 |  |  | 10 | 3 | 100% | 425 | 460 | 0 | 460 | 35 | 8.235%
2 | Sample Task 2 | First Phase Complete | 2009-09-26 | 2009-10-16 | 2009-09-24 | 2009-10-14 | 2009-09-24 | 2009-10-14 | 20 | 20 | 100% | 6150 | 7380 | 0 | 7380 | 1230 | 20%
3 | Sample Task 3 | Second Phase Complete | 2009-10-17 | 2009-10-30 | 2009-10-15 | 2009-11-15 | 2009-10-15 | 2009-10-28 | 13 | 31 | 83.33% | 440 | 330 | 125 | 455 | 15 | 3.409%
4 | Sample Task 4 | Second Phase Complete | 2009-10-31 | 2009-11-25 | 2009-11-16 | 2009-12-11 | 2009-11-16 | 2009-12-11 | 25 | 25 | 16.67% | 610 | 40 | 530 | 570 | -40 | -6.557%
5 | Sample Task 5 | Second Phase Complete | 2009-11-26 | 2009-12-15 | 2009-12-12 | 2009-12-31 | 2009-12-12 | 2009-12-31 | 19 | 19 | 0% | 400 | 0 | 400 | 400 | 0 | 0%
6 | Sample Task 6 | Third Phase Complete | 2009-12-16 | 2010-01-04 | 2010-01-01 | 2010-01-20 | 2010-01-01 | 2010-01-20 | 19 | 19 | 0% | 345 | 0 | 345 | 345 | 0 | 0%
7 | Sample Task 7 | Third Phase Complete | 2010-01-05 | 2010-01-20 | 2010-01-21 | 2010-02-05 | 2010-01-21 | 2010-02-05 | 15 | 15 | 0% | 9280 | 0 | 9280 | 9280 | 0 | 0%
8 | Sample Task 8 | Third Phase Complete | 2010-01-21 | 2010-02-10 | 2010-02-06 | 2010-02-26 | 2010-02-06 | 2010-02-26 | 20 | 20 | 0% | 6150 | 0 | 6150 | 6150 | 0 | 0%
9 | Sample Task 9 | Fourth Phase Complete | 2010-02-11 | 2010-02-27 | 2010-02-27 | 2010-03-15 | 2010-02-27 | 2010-03-15 | 16 | 16 | 0% | 4820 | 0 | 4820 | 4820 | 0 | 0%
10 | Sample Task 10 | Fourth Phase Complete | 2010-02-28 | 2010-03-15 | 2010-03-16 | 2010-04-15 | 2010-03-16 | 2010-03-31 | 15 | 30 | 0% | 160 | 0 | 160 | 160 | 0 | 0%
11 | [6 empty] | 2010-04-16 | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
12 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
13 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
14 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
15 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
16 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
17 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
18 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
19 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
20 | [6 empty] | - | - | - | - | 0% | 0 | 0 | 0 | 0 | 0 | 0%
Formulas:
Suggested Revised Start Date = IF([Actual or Revised End Date, row above]>0,[Actual or Revised End Date, row above]+1,"-")
Suggested Revised End Date = IF(AND([Suggested Revised Start Date]>0,[Baseline Duration]<>"-"),[Suggested Revised Start Date]+[Baseline Duration],"-")
Tasks feed milestones. Each task takes people and sometimes other resources to complete, all of which have a cost. Keep track of all your project's tasks here. This worksheet carries forward milestones from tab 2-Milestones and sends back the total percent complete for each milestone.
Important: If you add a task that was not thought of when the baseline was created (it happens), enter $0 for the baseline cost.
Important: This sheet uses data validation to ensure you can only enter percent complete in multiples of 25%. This is to help avoid "90% complete syndrome" by providing a visual cue. Turn data validation off if you would rather use your own percent completes.

## 4-Resources
Num | Resource Type | Resource Name | Rate | How Does the Resource Charge? | Role | Contact Phone Number | Is This Resource Needed Before the Next Reporting Period? | Will This Resource Be Taking Time Away from the Project Before the Next Reporting Period? | There is a Concern Around Availability for This Resource
1 | Person | John Appleseed | 45 | by hour | Project Manager | 4165552323 | YES | NO | NO
2 | Person | Mabel Wentworth | 35 | by hour | Business Analyst | 4165552121 | YES | YES | YES
3 | Person | Janice Feldstone | 150 | by day | Business Analyst | 4165552222 | YES | NO | NO
4 | Equipment | Hall Rental | 250 | by day | Presentation | 4165552323 | N/A | NO | -
5 | Equipment | Projection Unit | 15 | by hour | Presentation | 4165552198 | NO | NO | -
6 | Person | Elizabeth Smith | 1000 | by day | Tester | 4165552256 | NO | NO | -
7 | Person | David Altman | 60 | by hour | Tester | 4165559898 | NO | NO | -
8 | Person | Kirk Underwood | 55 | by hour | Developer | 4165552221 | YES | NO | NO
9 | Materials | Duct Tape | 3 | by quantity | Materials | N/A | N/A | NO | -
10 | Materials | Double A Batteries | 2 | by quantity | Materials | N/A | N/A | NO | -
11 | Contingency | Contingency Budget | 10000 | by quantity | Contingency Budget | N/A | NO | NO | -
12 | [8 empty] | -
13 | [8 empty] | -
14 | [8 empty] | -
15 | [8 empty] | -
-
-
-
It takes resources to get work done. Usually project resources are people, but materials and equipment factor into your budget as well. Use the following sheet to keep track of all your project resources, and show how much they cost. These costs will be used to calculate both your baseline budget and your actual costs as you move through your project.
You can also use this sheet to raise any flags about the availability of resources. If key resources are needed before the next reporting period, and they won't be available, there is a risk that work won't get done. Set the flag here and it will raise a yellow indicator on the project dashboard.

## 5-Costs
Milestone | Task | Resource | Baseline Effort or Units Expected | Actual Effort or Units Spent | What Percent Complete is this Resource on this Task? | Estimated Effort or Units Remaining | Baseline Cost Expected | Actual Cost Spent To Date | What Should Have Been Spent To Date | Estimated Cost Remaining
First Phase Complete | Sample Task 1 | John Appleseed | 2 | 2 | 100% | 0 | 90 | 90 | 90 | 0
First Phase Complete | Sample Task 1 | Mabel Wentworth | 2 | 3 | 100% | 0 | 70 | 105 | 70 | 0
First Phase Complete | Sample Task 1 | Hall Rental | 1 | 1 | 100% | 0 | 250 | 250 | 250 | 0
First Phase Complete | Sample Task 1 | Projection Unit | 1 | 1 | 100% | 0 | 15 | 15 | 15 | 0
First Phase Complete | Sample Task 2 | John Appleseed | 5 | 6 | 100% | 0 | 225 | 270 | 225 | 0
First Phase Complete | Sample Task 2 | Mabel Wentworth | 5 | 6 | 100% | 0 | 175 | 210 | 175 | 0
First Phase Complete | Sample Task 2 | Janice Feldstone | 5 | 6 | 100% | 0 | 750 | 900 | 750 | 0
First Phase Complete | Sample Task 2 | Elizabeth Smith | 5 | 6 | 100% | 0 | 5000 | 6000 | 5000 | 0
Second Phase Complete | Sample Task 3 | John Appleseed | 3 | 1 | 75% | 2 | 135 | 45 | 101.25 | 90
Second Phase Complete | Sample Task 3 | Mabel Wentworth | 3 | 1 | 75% | 1 | 105 | 35 | 78.75 | 35
Second Phase Complete | Sample Task 3 | Double A Batteries | 100 | 125 | 100% | 0 | 200 | 250 | 200 | 0
Second Phase Complete | Sample Task 4 | John Appleseed | 2 | 0.5 | 25% | 1 | 90 | 22.5 | 22.5 | 45
Second Phase Complete | Sample Task 4 | Mabel Wentworth | 2 | 0.5 | 25% | 1 | 70 | 17.5 | 17.5 | 35
Second Phase Complete | Sample Task 4 | Duct Tape | 150 |  | 0% | 150 | 450 | 0 | 0 | 450
Second Phase Complete | Sample Task 5 | John Appleseed | 5 |  | 0% | 5 | 225 | 0 | 0 | 225
Second Phase Complete | Sample Task 5 | Mabel Wentworth | 5 |  | 0% | 5 | 175 | 0 | 0 | 175
Third Phase Complete | Sample Task 6 | Kirk Underwood | 3 |  | 0% | 3 | 165 | 0 | 0 | 165
Third Phase Complete | Sample Task 6 | David Altman | 3 |  | 0% | 3 | 180 | 0 | 0 | 180
Third Phase Complete | Sample Task 7 | John Appleseed | 8 |  | 0% | 8 | 360 | 0 | 0 | 360
Third Phase Complete | Sample Task 7 | Elizabeth Smith | 8 |  | 0% | 8 | 8000 | 0 | 0 | 8000
Third Phase Complete | Sample Task 7 | David Altman | 8 |  | 0% | 8 | 480 | 0 | 0 | 480
Third Phase Complete | Sample Task 7 | Kirk Underwood | 8 |  | 0% | 8 | 440 | 0 | 0 | 440
Third Phase Complete | Sample Task 8 | John Appleseed | 5 |  | 0% | 5 | 225 | 0 | 0 | 225
Third Phase Complete | Sample Task 8 | Mabel Wentworth | 5 |  | 0% | 5 | 175 | 0 | 0 | 175
Third Phase Complete | Sample Task 8 | Janice Feldstone | 5 |  | 0% | 5 | 750 | 0 | 0 | 750
Third Phase Complete | Sample Task 8 | Elizabeth Smith | 5 |  | 0% | 5 | 5000 | 0 | 0 | 5000
Fourth Phase Complete | Sample Task 9 | Janice Feldstone | 4 |  | 0% | 4 | 600 | 0 | 0 | 600
Fourth Phase Complete | Sample Task 9 | Elizabeth Smith | 4 |  | 0% | 4 | 4000 | 0 | 0 | 4000
Fourth Phase Complete | Sample Task 9 | Kirk Underwood | 4 |  | 0% | 4 | 220 | 0 | 0 | 220
Fourth Phase Complete | Sample Task 10 | John Appleseed | 2 |  | 0% | 2 | 90 | 0 | 0 | 90
Fourth Phase Complete | Sample Task 10 | Mabel Wentworth | 2 |  | 0% | 2 | 70 | 0 | 0 | 70
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
--- | [6 empty] | 0 | 0 | 0 | 0
This is your detailed working area. Once you've set your milestones, tasks and resources, this sheet will keep track of all the fine details of how much your work will cost. Select one of your tasks from the dropdown list. That will automatically enter the milestone it's attached to. Choose a resource from the drop down, and enter how many units you expect this resource to charge to that particular task. If the resource charges in hours, enter the number of hours. If the resource charges by day, enter the number of days. As you fill this in, tabs 2-Milestones and 3-Tasks will automatically update with baseline information.
Each week of your project, come back and update the actual effort or units spent, and how far along the resource is in completing the task. Check in with your resource and find out how many more units of time they'll need to get the task done.
You can expect this sheet to get quite large, but you can use the autofilter buttons to keep the view manageable (filter by milestone or task for example).

## 6-Change Requests
Num | Change Request Document Name | Summary of Changes | Date Submitted (dd-mmm-yyyy) | Name of Requestor | Cost Impact ($) | Schedule Impact (Days) | Have All Stakeholders Approved This Change Request? | Final Approval Date (dd-mmm-yyyy) | Status
1 | cr-001-change-document1 | Sample change summary. | 2009-12-15 | John Appleseed | 10000 | 20 | YES | 2010-01-25 | Accepted
2 | cr-002-change-document2 | Sample change summary. | 2009-12-25 | John Appleseed | 15000 | 15 | NO |  | Pending
If you need to go back and redo work that fed a completed (and approved) milestone, or if you need to change the scope of the work that you've undertaken, you should raise a change request. Change requests help to keep all of the stakeholders aware of changes to the project, and give them an opportunity to voice any concerns that could affect their area of interest. It's important to keep track of any change requests throughout the project, because they invariably have a cost in both money and time.
If any change requests have been raised but have not been approved, it will raise a red flag on the dashboard.
Important: Once you've added a change request to the log, be sure to go back to tab 1-Instructions and update the Baseline Cost, and update tabs 3-Milestones, 4-Tasks and 5-Costs.

## 7-Quality
Num | Document Name | Who will create this document? | Who will review this document? | Who will approve this document? | When should this document be approved? (dd-mmm-yyyy) | Created | Reviewed | Approved | Approval is on track (fill down)
1 | Sample Project Charter | John Appleseed | Mabel Wentworth | Janice Feldstone | 2009-11-08 | x | x |  | NO
2 | Sample Quality Plan | John Appleseed | Mabel Wentworth | Janice Feldstone | 2009-11-18 | x | x | x | YES
3 | Sample Project Workbook | John Appleseed | Mabel Wentworth | Janice Feldstone | 2009-12-15 | x | x | x | YES
4 | Sample Requirements | John Appleseed | Mabel Wentworth | Janice Feldstone | 2009-12-25 | x |  |  | NO
5 | Sample High Level Design | John Appleseed | Mabel Wentworth | Janice Feldstone | 2010-01-15 | x |  |  | YES
6 | Sample Detailed Design | John Appleseed | Mabel Wentworth | Janice Feldstone | 2010-01-20 | x |  |  | YES
7 | Sample Test Plan | John Appleseed | Mabel Wentworth | Janice Feldstone | 2010-02-15 |  |  |  | YES
8 | Sample User Documentation | John Appleseed | Mabel Wentworth | Janice Feldstone | 2010-02-20 |  |  |  | YES
9 | Sample Code Walkthrough | John Appleseed | Mabel Wentworth | Janice Feldstone | 2010-03-15 |  |  |  | YES
10 | Sample Project Sign Off | John Appleseed | Mabel Wentworth | Janice Feldstone | 2010-03-20 |  |  |  | YES
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
This tab will help to ensure all output quality is to the standards of the stakeholders. Use this sheet to note down all the documents that need to be created during the course of the project, and identify, by name, the people who will need to create, review and approve each document.
Then, put an 'X' under "Created", "Reviewed" and "Approved" once those activities are done. Simple!
"Approval is on track" is a simple comparison. If the document should have been approved by now, but has not been, then approval is not on track. Otherwise, the chance remains that approval is pending. This field is used to calculate the dashboard KPI. This KPI is binary so cannot have a yellow status with this project book.

## 8-Issues
Num | Issue Description | Date Reported (dd-mmm-yyyy) | Severity | Report This Issue on Dashboard? (1, 2, 3) | Person Responsible | Estimated Resolution Date (dd-mmm-yyyy) | Current Activity | Is this Issue Open or Closed? | Resolution | Closed Date (dd-mmm-yyyy) | Days to Close (Fill Down)
1 | Sample Issue 1 | 2009-11-01 | Blocking |  | John Appleseed | 2010-01-30 | Description of what's being done to resolve Sample Issue 1. | Closed | Description of how Sample Issue 1 was resolved. | 2009-12-15 | 44
2 | Sample Issue 2 | 2009-11-12 | Important |  | Mabel Wentworth | 2009-12-08 | Description of what's being done to resolve Sample Issue 2. | Open |  |  | -
3 | Sample Issue 3 | 2009-11-12 | Take Note |  | John Appleseed | 2009-11-15 | Description of what's being done to resolve Sample Issue 3. | Closed | Description of how Sample Issue 3 was resolved. | 2009-11-18 | 6
4 | Sample Issue 4 | 2009-11-15 | Blocking | 1 | Mabel Wentworth | 2010-01-12 | Description of what's being done to resolve Sample Issue 4. | Open |  |  | -
5 | Sample Issue 5 | 2009-12-25 | Blocking | 2 | John Appleseed | 2010-02-15 | Description of what's being done to resolve Sample Issue 5. | Open |  |  | -
6 | Sample Issue 6 | 2009-11-18 | Take Note |  | Mabel Wentworth | 2009-11-25 | Description of what's being done to resolve Sample Issue 6. | Closed | Description of how Sample Issue 6 was resolved. | 2009-12-15 | 27
7 | Sample Issue 7 | 2009-11-25 | Take Note |  | John Appleseed | 2010-01-12 | Description of what's being done to resolve Sample Issue 7. | Closed | Description of how Sample Issue 7 was resolved. | 2010-01-02 | 38
8 | Sample Issue 8 | 2009-12-18 | Blocking | 3 | Janice Feldstone | 2010-02-18 | Description of what's being done to resolve Sample Issue 8. | Open |  |  | -
9 | Sample Issue 9 | 2009-12-25 | Important |  | Janice Feldstone | 2010-02-25 | Description of what's being done to resolve Sample Issue 9. | Open |  |  | -
10 | Sample Issue 10 | 2009-01-02 | Important |  | John Appleseed | 2010-01-25 | Description of what's being done to resolve Sample Issue 10. | Open |  |  | -
11 | [10 empty] | -
12 | [10 empty] | -
13 | [10 empty] | -
14 | [10 empty] | -
15 | [10 empty] | -
16 | [10 empty] | -
17 | [10 empty] | -
18 | [10 empty] | -
19 | [10 empty] | -
20 | [10 empty] | -
Use this tab to track all of your project issues. Tracking issues is important to projects as it ensures the project team knows what needs to be resolved for work to keep going. Also, keeping a record of closed issues is helpful in case the issue crops up again; the team can look up the resolution and fix it faster the next time.
The severity of an issue is important to know: "Blocking" means some or all work can't continue until the issue is resolved. "Important" means you can keep working, but it will likely soon become a blocking issue. "Take Note" means work can keep going but you'll want to resolve this issue once others are taken care of.
Make sure to keep the issue dates current. Management will want to know that issues are being closed soon after they're identified. For the dashboard, enter '1', '2' and '3' to choose the top issues you'd like to report on.
Important: Once you've entered an issue into this register, never delete it, as even closed issues are important to keep track of. Simply mark the issue as closed, make sure to enter how you solved the problem, and it will no longer show up as an open issue on the dashboard.

## 9-Risks
Num | Is This Risk Still Valid? | Risk Event | Likelihood (1-4) | Impact (1-4) | Current Score (Fill Down) | Consequence | Approach | Strategy | New Likelihood (1-4) | New Impact (1-4) | New Score (Fill Down) | Person Responsible for Action | Date Action Due (dd-mmm-yyyy)
1 | Yes | Sample Risk 1 | 3 | 4 | 20 | Describe what will happen if Sample Risk 1 comes to pass. | Mitigate | Briefly describe how you intend to deal with Sample Risk 1. | 2 | 2 | 9 | John Appleseed | 2010-01-15
2 | Yes | Sample Risk 2 | 4 | 4 | 25 | Describe what will happen if Sample Risk 2 comes to pass. | Transfer | Briefly describe how you intend to deal with Sample Risk 2. | 4 | 1 | 10 | Mabel Wentworth | 2010-01-25
3 | No | Sample Risk 3 | 3 | 4 | 20 | Describe what will happen if Sample Risk 3 comes to pass. | Mitigate | Briefly describe how you intend to deal with Sample Risk 3. | 2 | 2 | 9 | John Appleseed | 2010-01-18
4 | Yes | Sample Risk 4 | 3 | 3 | 16 | Describe what will happen if Sample Risk 4 comes to pass. | Mitigate | Briefly describe how you intend to deal with Sample Risk 4. | 1 | 2 | 6 | Mabel Wentworth | 2010-02-15
5 | Yes | Sample Risk 5 | 3 | 4 | 20 | Describe what will happen if Sample Risk 5 comes to pass. | Mitigate | Briefly describe how you intend to deal with Sample Risk 5. | 2 | 2 | 9 | John Appleseed | 2010-02-02
6 | Yes | Sample Risk 6 | 4 | 4 | 25 | Describe what will happen if Sample Risk 6 comes to pass. | Avoid | Briefly describe how you intend to deal with Sample Risk 6. | 1 | 1 | 4 | Mabel Wentworth | 2010-01-20
7 | No | Sample Risk 7 | 2 | 4 | 15 | Describe what will happen if Sample Risk 7 comes to pass. | Mitigate | Briefly describe how you intend to deal with Sample Risk 7. | 2 | 3 | 12 | John Appleseed | 2010-01-25
8 | Yes | Sample Risk 8 | 3 | 2 | 12 | Describe what will happen if Sample Risk 8 comes to pass. | Mitigate | Briefly describe how you intend to deal with Sample Risk 8. | 2 | 1 | 6 | Janice Feldstone | 2010-02-08
9 | Yes | Sample Risk 9 | 3 | 3 | 16 | Describe what will happen if Sample Risk 9 comes to pass. | Mitigate | Briefly describe how you intend to deal with Sample Risk 9. | 2 | 2 | 9 | Janice Feldstone | 2010-02-09
10 | No | Sample Risk 10 | 2 | 2 | 9 | Describe what will happen if Sample Risk 10 comes to pass. | Accept | Briefly describe how you intend to deal with Sample Risk 10. | 2 | 2 | 9 | John Appleseed | 2010-02-20
11 |  |  |  |  | 0 | [5 empty] | 0
12 |  |  |  |  | 0 | [5 empty] | 0
13 |  |  |  |  | 0 | [5 empty] | 0
14 |  |  |  |  | 0 | [5 empty] | 0
15 |  |  |  |  | 0 | [5 empty] | 0
16 |  |  |  |  | 0 | [5 empty] | 0
17 |  |  |  |  | 0 | [5 empty] | 0
18 |  |  |  |  | 0 | [5 empty] | 0
19 |  |  |  |  | 0 | [5 empty] | 0
20 |  |  |  |  | 0 | [5 empty] | 0
This tab will keep track of all of the risks to your project. For each risk your team can identify, rate the likelihood and impact on a scale of 1-4, where 1 is low likelihood of a risk event happening or impact if it does happen and 4 is very high likelihood or impact. This worksheet will colour code your risks by order of severity.
Then, select your approach from the drop down menu for each risk, and briefly note down your strategy for dealing with that risk. Now rate the risk again. Do you think the likelihood and impacts have decreased? If so, use the same scale of 1-4 for your rating. This worksheet will calculate a risk score for you both before and after your approach.
Important: If a risk is no longer valid, don't delete it. It's important to keep a running track of any risks you may have faced, so that you know how you dealt with it while it was active. If a risk is no longer valid, flag it so in the second column. That will keep it from showing up on the dashboard. Then you still have a record of your approach and strategy in case it rears its ugly head again.

## 10-Status Report
Management will expect to be kept informed of your project, so it's a good idea to provide them all the important information points on your project in one easy-to-read report on a regular basis (at least once a month). Following the instructions on this tab will provide the final pieces of information to your dashboard.
Ideally these should be the top three things your team accomplished since the last report. Avoid making achievements sound technical. Focus on milestones that you completed, or other "big deal" events. | Top Three Achievements for This Reporting Period |  |  |  |  | Ideally these three things should be your achievements for the next report. When you go to prepare your next report you should be able to copy / paste these items right into your achievements to the left. Remember that this report is meant to set your management's expectations so be careful not to overpromise on things you might not be able to deliver. |  |  | Top Three Things to Expect for Next Reporting Period
| First sample achievement. | [7 empty] | First thing to expect next period.
| Second sample achievement. | [7 empty] | Second thing to expect next period.
| Third sample achievement. | [7 empty] | Third thing to expect next period.
Project Reporting Range (delete, change and add as appropriate)
|  | Current | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Project Reporting Range: It's important to keep a running history of information from each status report for comparison. Before you prepare your first report, enter the full expected date range of your project below (change, delete or add dates as needed). Afterwards, each time you prepare a report, copy the grey outlined section below when you are ready to prepare your status report and PASTE VALUES under the appropriate period. That will carry over your previous data for use by the project dashboard as well as the EVA calculations below. Be very careful to PASTE VALUES otherwise you'll copy over formulas which could contaminate your results. | Performance Indicators for Dashboard
| Stakeholder Involvement | 3 | Project Reporting Range (delete, change and add as appropriate) Sep: 1; Project Reporting Range (delete, change and add as appropriate) Oct: 1; Project Reporting Range (delete, change and add as appropriate) Nov: 2; Project Reporting Range (delete, change and add as appropriate) Dec: 1
| Project Schedule | 2 | Project Reporting Range (delete, change and add as appropriate) Sep: 1; Project Reporting Range (delete, change and add as appropriate) Oct: 1; Project Reporting Range (delete, change and add as appropriate) Nov: 2; Project Reporting Range (delete, change and add as appropriate) Dec: 2
| Project Budget | 2 | Project Reporting Range (delete, change and add as appropriate) Sep: 1; Project Reporting Range (delete, change and add as appropriate) Oct: 1; Project Reporting Range (delete, change and add as appropriate) Nov: 2; Project Reporting Range (delete, change and add as appropriate) Dec: 2
| Project Scope | 3 | Project Reporting Range (delete, change and add as appropriate) Sep: 1; Project Reporting Range (delete, change and add as appropriate) Oct: 1; Project Reporting Range (delete, change and add as appropriate) Nov: 1; Project Reporting Range (delete, change and add as appropriate) Dec: 3
| Resource Availability | 2 | Project Reporting Range (delete, change and add as appropriate) Sep: 1; Project Reporting Range (delete, change and add as appropriate) Oct: 1; Project Reporting Range (delete, change and add as appropriate) Nov: 1; Project Reporting Range (delete, change and add as appropriate) Dec: 2
| Quality Performance Indicator | 2 | Project Reporting Range (delete, change and add as appropriate) Sep: 1; Project Reporting Range (delete, change and add as appropriate) Oct: 1; Project Reporting Range (delete, change and add as appropriate) Nov: 1; Project Reporting Range (delete, change and add as appropriate) Dec: 2
Cost Metrics for Dashboard
| Baseline Cost | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
| Expected Cost to Date | 6995 | Project Reporting Range (delete, change and add as appropriate) Sep: 1000; Project Reporting Range (delete, change and add as appropriate) Oct: 2000; Project Reporting Range (delete, change and add as appropriate) Nov: 3500; Project Reporting Range (delete, change and add as appropriate) Dec: 10000
| Actual To Date | 8210 | Project Reporting Range (delete, change and add as appropriate) Sep: 850; Project Reporting Range (delete, change and add as appropriate) Oct: 1500; Project Reporting Range (delete, change and add as appropriate) Nov: 3200; Project Reporting Range (delete, change and add as appropriate) Dec: 8210
| Estimate To Complete | 21810 | Project Reporting Range (delete, change and add as appropriate) Sep: 24000; Project Reporting Range (delete, change and add as appropriate) Oct: 22000; Project Reporting Range (delete, change and add as appropriate) Nov: 23000; Project Reporting Range (delete, change and add as appropriate) Dec: 21810
| Total Expected Project Cost | 30020 | Project Reporting Range (delete, change and add as appropriate) Sep: 24150; Project Reporting Range (delete, change and add as appropriate) Oct: 23500; Project Reporting Range (delete, change and add as appropriate) Nov: 21800; Project Reporting Range (delete, change and add as appropriate) Dec: 16790
| Variance in Dollars | -5020 | Project Reporting Range (delete, change and add as appropriate) Sep: 850; Project Reporting Range (delete, change and add as appropriate) Oct: 1500; Project Reporting Range (delete, change and add as appropriate) Nov: 3200; Project Reporting Range (delete, change and add as appropriate) Dec: 8210
| Variance in Percent | -20.08% | Project Reporting Range (delete, change and add as appropriate) Sep: 3.4%; Project Reporting Range (delete, change and add as appropriate) Oct: 6%; Project Reporting Range (delete, change and add as appropriate) Nov: 12.8%; Project Reporting Range (delete, change and add as appropriate) Dec: 32.84%
| Percent of Project Complete | 27.35% | Project Reporting Range (delete, change and add as appropriate) Sep: 3.52%; Project Reporting Range (delete, change and add as appropriate) Oct: 6.383%; Project Reporting Range (delete, change and add as appropriate) Nov: 14.68%; Project Reporting Range (delete, change and add as appropriate) Dec: 48.9%
Issue Metrics for Dashboard
| Total Open Issues: | 6 | Project Reporting Range (delete, change and add as appropriate) Sep: 2; Project Reporting Range (delete, change and add as appropriate) Oct: 5; Project Reporting Range (delete, change and add as appropriate) Nov: 4; Project Reporting Range (delete, change and add as appropriate) Dec: 6
| Total Open Blocking Issues: | 3 | Project Reporting Range (delete, change and add as appropriate) Sep: 0; Project Reporting Range (delete, change and add as appropriate) Oct: 1; Project Reporting Range (delete, change and add as appropriate) Nov: 3; Project Reporting Range (delete, change and add as appropriate) Dec: 2
| Average Days to Close: | 28.75 | Project Reporting Range (delete, change and add as appropriate) Sep: 15; Project Reporting Range (delete, change and add as appropriate) Oct: 10; Project Reporting Range (delete, change and add as appropriate) Nov: 18; Project Reporting Range (delete, change and add as appropriate) Dec: 28.75
Risk Metrics for Dashboard
| Risk Score Before Plan: | 134 | Project Reporting Range (delete, change and add as appropriate) Sep: 134; Project Reporting Range (delete, change and add as appropriate) Oct: 134; Project Reporting Range (delete, change and add as appropriate) Nov: 134; Project Reporting Range (delete, change and add as appropriate) Dec: 134
| Risk Score After Plan: | 53 | Project Reporting Range (delete, change and add as appropriate) Sep: 53; Project Reporting Range (delete, change and add as appropriate) Oct: 53; Project Reporting Range (delete, change and add as appropriate) Nov: 53; Project Reporting Range (delete, change and add as appropriate) Dec: 53
|  |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Earned Value Analysis (EVA): If you wish to take Earned Value Analysis further, it's outside the scope of this workbook. However, many of the fields used in EVA have been calculated for you below. Simply fill the fields across your project timeline (including the dates) and you can perform the analysis as you wish. | Planned Value (PV, BCWS) |  | 1000 | 2000 | 3500 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual Cost (AC, ACWP) |  | 850 | 1500 | 3200 | 8210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Budget at Completion (BAC, Baseline Cost) |  | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
| Percent of Project Complete (PPC) |  | 3.52% | 6.383% | 14.68% | 48.9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Earned Value (EV): BAC * PPC |  | 879.9172 | 1595.7447 | 3669.7248 | 12224.5384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cost Variance (CV): EV - AC |  | 29.9172 | 95.7447 | 469.7248 | 4014.5384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Schedule Variance (SV): EV - PV |  | -120.0828 | -404.2553 | 169.7248 | 2224.5384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cost Performance Index (CPI): EV / AC |  | 1.0352 | 1.0638 | 1.1468 | 1.489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Schedule Performance Index (SPI): EV / PV |  | 0.87992 | 0.79787 | 1.0485 | 1.2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimate at Completion (EAC): BAC / CPI |  | 24150 | 23500 | 21800 | 16790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Estimate at Completion (EAC): AC + (BAC - EV) |  | 24970.0828 | 24904.2553 | 24530.2752 | 20985.4616 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
| Estimate to Complete (ETC): (BAC / CPI) - AC |  | 23300 | 22000 | 18600 | 8580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Variance at Completion (VAC): BAC - (BAC / CPI) |  | 850 | 1500 | 3200 | 8210 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000

## DASHBOARD
Project Summary |  |  |  | Objectives |  |  | Project Risk
Report Date: |  | 2010-01-03 |  |  | [Enter your top project objective]
Project Name: |  | [Enter your project's name] |  |  | [Enter a second project objective]
Project Number: |  | [Enter the number for your project] |  |  |  |  | 
Project Sponsor: |  | [Enter your project sponsor's name] |  |  | [Enter a third project objective]
Project Manager: |  | [Enter your project manager's name]
Project Progress | -15.12% | [5 empty] | Key Performance Indicators |  | Sep | Oct | Nov | Dec | Current Trend
[7 empty] | Overall Project Performance |  | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | Stakeholder Involvement |  | #REF! | #REF! | #REF! | #REF! | #REF!
Financial Summary
[7 empty] | Project Schedule |  | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | Project Budget |  | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | Project Scope |  | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | Resource Availability |  | #REF! | #REF! | #REF! | #REF! | #REF!
[7 empty] | Anticipated Quality |  | #REF! | #REF! | #REF! | #REF! | #REF!
Top Current Issues | Num | Issue | Current Activity |  |  | Days Open | Latest Achievements | Achievement
| 4 | Sample Issue 4 | Description of what's being done to resolve Sample Issue 4. |  |  | 49 |  | First sample achievement.
| 5 | Sample Issue 5 | Description of what's being done to resolve Sample Issue 5. |  |  | 9 |  | Second sample achievement.
| 8 | Sample Issue 8 | Description of what's being done to resolve Sample Issue 8. |  |  | 16 |  | Third sample achievement.
Issue History | [6 empty] | Highlights Expected for Next Report | Activity
First thing to expect next period.
Second thing to expect next period.
Third thing to expect next period.
Project Summary. This section shows the basic information about the project, and most importantly, the date of this report. |  |  |  | Project Objectives. These objectives should be confirmed during every status review to make sure they're still valid. |  |  | Project Risks. The chart shows, by counting, how many low, medium, high and very high risks could create problems for the project. The slider at left points to the overall risk level of the project.
Project Progress. This section shows the baseline schedule broken down by phases (milestone dates) against the revised schedule. | [6 empty] | The Key Performance Indicators show how well different aspects of the project are doing, and gives a trend indicator on whether or not the indicator has improved, stayed the same or gotten worse since the last report. Measurements are as follows: Stakeholder Involvement: Green - stakeholders are actively engaged; Yellow - new stakeholders have been identified this period; Red - key stakeholders be may not available when needed next period. Project Schedule: Green - the project is expected to stay within 10% of the baseline; Yellow - the project is expected to stay within 25% of the baseline; Red - the project is expected to exceed 25% of the baseline. Project Budget: Green - the project is expected to stay within 10% of the baseline; Yellow - the project is expected to stay within 25% of the baseline; Red - the project is expected to exceed 25% of the baseline. Project Scope: Green - scope is considered managable; Yellow - there are questions around project objectives; Red - there are open and unapproved change requests. Resource Availability: Anticipated Quality: Green - All due quality documents are approved; Yellow - Up to 20% of due quality documents are not approved; Red - More than 20% of due quality documents are not approved.
Financial Summary. Use this section to monitor the project financials. The stacked bar is a sum of the actual cost of the project to date, and the estimate remaining to complete the project. This compares against the original baseline estimate for the project to show whether the project is costing more or less than expected. The variance line shows how far off the project is from baseline cost in percent.
Top Issues. This section shows the top issues that need to be resolved on the project. The project manager can use this section to ask management for help to clear blocking issues, and management can keep track of how long these issues have been open. | [6 empty] | Project Manager's Commentary. This section is for the project manager to inform management of the top achievements accomplished since the last status report. It is also a place to advise management on what to expect for the next report.
Issue History. This chart shows the number of open issues over time for the last four months of the project. It also shows how many blocking issues the project has encountered, and how long issues take to close on average.

## Scratchpad - Not For Use
The scratchpad is an important part of this project book and should not be modified. This tab is used to create the dashboard. By using a scratchpad instead of macros this book eliminates the worry that macro viruses may be inadvertently activated, and prevents annoying popups everytime you open the file. You are free to edit this tab, but advanced knowledge of Excel is essential before doing so.
Rightmost Valid Range (for EVA) | 11 | '10-Status Report'!
Leftmost Valid Range (for EVA) | 8
Bottommost Valid Range (for Milestones) | 11
Array Milestones | '3-Tasks'!$C$1:$C$11
Array Baseline Start Date | '3-Tasks'!$D$1:$D$11
Array Baseline End Date | '3-Tasks'!$E$1:$E$11
Array Revised Start Date | '3-Tasks'!$F$1:$F$11
Array Revised End Date | '3-Tasks'!$G$1:$G$11
Most Recent Dates | #REF! | #REF! | #REF! | #REF!
Baseline Cost | #REF! | #REF! | #REF! | #REF! | This section takes the financial data you copied across on the Instructions tab, and only pulls off the last four months. It's used to create the dashboard financials.
Actual To Date | #REF! | #REF! | #REF! | #REF!
Estimate To Complete | #REF! | #REF! | #REF! | #REF!
Total Project Cost | #REF! | #REF! | #REF! | #REF!
Variance | #REF! | #REF! | #REF! | #REF!
Total Open Issues | #REF! | #REF! | #REF! | #REF! | This section takes the issues you copied across on the Instructions tab, and only pulls off the last four months. It's used to create the dashboard issues chart.
Total Blocking Issues | #REF! | #REF! | #REF! | #REF!
Average Days to Close | #REF! | #REF! | #REF! | #REF!
First Issue | 4 |  |  |  | This section copies over the top three issues you selected on the Issues tab. These issues go into the dashboard.
Second Issue | 5
Third Issue | 8
Key Performance Indicators
Total Schedule Variance | -15.12%
Stakeholder Involvement | #REF! | #REF! | #REF! | #REF!
Project Schedule | #REF! | #REF! | #REF! | #REF!
Project Budget | #REF! | #REF! | #REF! | #REF!
Project Scope | #REF! | #REF! | #REF! | #REF!
Resource Availability | #REF! | #REF! | #REF! | #REF!
Quality Performance Indicator | #REF! | #REF! | #REF! | #REF!
Risks
Low | 1
Moderate | 5
High | 1
Very High | 0
Overall | 53
Database Criteria
Issues Criteria |  |  |  |  | Excel uses these cells to get criteria used in database calculations on the Issues tab.
Severity | Is this Issue Open or Closed? | Report This Issue on Dashboard? (1, 2, 3) | Report This Issue on Dashboard? (1, 2, 3) | Report This Issue on Dashboard? (1, 2, 3)
Blocking | Open | 1 | 2 | 3
Risks Criteria |  |  |  |  | Excel uses these cells to get criteria used in database calculations on the Risks tab.
Is This Risk Still Valid? | New Score (Fill Down) | New Score (Fill Down)
Yes | >=0 | <=4
Is This Risk Still Valid? | New Score (Fill Down) | New Score (Fill Down)
Yes | >=5 | <=9
Is This Risk Still Valid? | New Score (Fill Down) | New Score (Fill Down)
Yes | >=10 | <=16
Is This Risk Still Valid? | New Score (Fill Down) | New Score (Fill Down)
Yes | >=17 | <=25
Milestones Criteria |  |  |  |  | Excel uses these cells to get criteria used in database calculations on the Milestones tab.
Which of your Milestones Does This Task Work Towards?
Yes