VDI Project Charter Template

Introduction: How to Use This Tool

A project charter serves several important functions. It organizes the project so that you can make efficient and effective resource allocation decisions. It also communicates important details on the project purpose, scope definition, and the project parameters.

To use this template, simply modify or delete all information colored grey or blue, and be sure to convert the remaining text to black before printing or sending. In addition to the fields and sections below, other tables and charts can be inserted in order to provide more specific information related to your VDI implementation.

This template should be used as a living document to carry the project through from pilot to implementation. All gray text represents sample text for a pre-pilot charter, and should be modified after the pilot to represent the implementation plan. Blue text represents pre-implementation text, and should reflect the results of the pilot in terms of how they will affect the implementation. The template has been filled with example text representing an organization that is looking to implement VDI to replace expensive take-home laptops.

Project title: [Organization]’s VDI Implementation Project

The project title or project name is often overlooked, but is a critical identity-building tool for the project team. The project title should describe the project’s purpose, but also contain some reference to the company and/or project team.

Project Sponsor: Joe Smith, IT Manager; jsmith@organizationname.com

Version: 0.9

Date: January 23, 2013

Projected Start and End Dates: June 25, 2013 to September 25, 2013

Although you may not know every date at this stage of the project, the start date and/or end date have usually been identified. These can be critical to staffing the project and allocating resources.

Table of Contents

1. Definitions and Abbreviations	4

2. Project Overview	5

3. Background	5

4. Project Organization	6

5. Project Purpose	7

6. Scope Definition	9

7. High Level Risk Assessment	10

8. Key Deliverables	11

9. High-Level Budget	13

10. Lessons Learned and Modifications	14

11.  Projected Timeline	15

1. Definitions and Abbreviations

It can be helpful to include definitions and acronyms that will be used throughout the document, which readers may or may not be familiar with. Some examples include:

- Desktop Virtualization: Desktop virtualization separates the management and operation of desktop applications and operating systems (OS) from physical desktop machines through the various layers of virtual abstraction. These virtual desktops are remote accessed from a user access device (i.e. PC, laptop, thin client, or mobile device).

- ITS: Information Technology Services

- PMO: Project Management Office

- RFP: Request for Proposal

- VDI: Virtual Desktop Infrastructure: Allows a full desktop to be presented to an access device from the server, where a virtual machine is hosted for each user.

- Etc.

2. Project Overview

Giving an overview of the planned implementation will help to focus and clarify the rest of the document

As part of [organization]’s standard four-year hardware refresh cycle, the Information Technology Department (IT) is planning to pilot the deployment of VDI solutions to applicable candidates. This will include deployment of thin clients to the users. Consistent monitoring and surveying practices will be used throughout the process in order to gauge success; and pending results, a full scale implementation will be rolled out.

3. Background

Providing background information on the current infrastructure and issues that you are attempting to resolve will provide context to the project.

The past five years have shown a steady increase in the number of laptops being deployed to employees who wish to have more mobility and flexibility in the choice of where and when they work. Currently, [x number] of employees use a company deployed laptop as their primary workstation. The cost of these laptops, as well as the risks associated with data loss on these devices, has necessitated an investigation into alternative solutions.

As well, more and more employees are choosing to use their own devices, such as tablets and smartphones, to perform work tasks. Currently, there are over [x number] of such devices used on a regular basis in [organization]. Most technological forecasts predict the utilization of these devices to sharply increase over the next year. In order to respond to these trends, IT needs a better way to support work-related applications on tablets and smartphones, as well as a way to ensure the security of confidential data.

IT has determined that approximately 25% of the current workforce would be better served by a Virtual Desktop Infrastructure solution. To that end, IT is planning to deploy a 30 seat pilot, and pending that success will implement a full scale implementation coordinated with our standard four year refresh cycle.

4. Project Organization

This section describes the roles of those involved in the project. It includes a listing of each person involved and what role each will play. These roles may include the following:

| Role | Name | Responsibilities |
| --- | --- | --- |
| Project Sponsor This is often the person who initiated the VDI project and is ultimately responsible for it. |  | - Retain overall responsibility of the project - Approve this charter and all deliverables - Provide funding |
| Project Manager This person is responsible for implementing the project plan. |  | - Coordinate resources and activities - Resolve issues and risks that appear |
| Change Officer This person is responsible for managing the scope of the project and providing first-level approval to any changes. |  | - Manages Scope |
| Business Unit Representative These people represent their business departments or business functions within the project team, and have authority from their departments to make decisions on their behalf. |  |  |
| Business Unit Representative |  |  |
| Business Unit Representative |  |  |
| External Resources Certain consultants or key external service providers may need to be identified. |  |  |
| Internal Resources Anyone else inside the company who is critical to project competition should be identified here, such as the Business Analyst, Requirements Analyst, etc. |  |  |

5. Project Purpose

Project Goals:

A list and description of the goals that the VDI project is expected to achieve should be included here. Goals should be prioritized as high (H), medium (M) or low (L).

| Goal | Priority |
| --- | --- |
| Secure a VDI solution, and demonstrate a proof of concept and subsequent pilot. | H ¦ M ¦ L |
| Assess pilot results in order to determine if wide spread deployment of VDI would be an effective solution. | H ¦ M ¦ L |
| Identify a solution that will equal or improve upon existing computer services currently offered, including: |  |
| - The ability to have a quick and responsive desktop. | H ¦ M ¦ L |
| - The ability to use [Application A] efficiently and effectively. | H ¦ M ¦ L |
| - The ability to use a tablet to improve mobility and flexibility. | H ¦ M ¦ L |
| Identify a solution that will enable IT staff to: |  |
| - Reduce the time and effort required to roll out changes and updates to software. | H ¦ M ¦ L |
| - Quickly respond to changes and updates to the operating systems and applications. | H ¦ M ¦ L |
| - Evaluate the solution’s impact on back end servers, storage, switches and network computing. | H ¦ M ¦ L |

Critical Success Factors:

Critical success factors are qualitative elements that determine the success of your project. Several VDI examples are included below:

| Category | Success Factor |
| --- | --- |
| Visuals and Graphics | Users should be able to modify their screen resolution and experience clear graphics and smooth animations. |
| Peripherals | Users should be able to use all peripherals they need, including USB storage devices and printers. |
| User Mobility | Users should be able to transition between devices and locations, and securely access their data and applications without delays or compatibility issues. |
| Personalization | Users should be able to make persistent customizations to their desktop environment, including application configurations and user preferences. |
| Business Continuity | In the event of a disaster, users should be able to continue working on their virtual desktop without issue. |
| Storage Requirements | Storage requirements should be kept low by minimizing storage of duplicate OS data. |
| Desktop Allocation | It should be simple and quick to deploy new desktops. |
| System Management | Updates and roll-outs to the system should be able to be done centrally, without the need to touch each desktop individually. |

6. Scope Definition

Project Scope clearly indicates what issues and topics will and will not be addressed during the project.

You may wish to consider the following areas when determining the scope of your VDI project:

Project Scope Is (Includes):

These tasks are all within the scope of the project and will be resolved.

- Creating guidelines regarding which workers will be best served by a VDI solution.

- Replace 30 desktop PC’s with Wyse thin clients

- Developing a support plan including new roles and responsibilities of IT units.

- Developing a communication plan to provide guidelines for informing new users about the changes that VDI brings.

Project Scope Is Not (Excludes):

These tasks are not within the scope of the project and will not be addressed.

- Funding upgrades to any applications that do not work as expected with VDI

- Supporting BYOD and employee-owned mobile devices. This will be reassessed in 12 months.

Scope Change Control Procedures:

A scope change control procedure can help to control the scope of the project from growing to an unmanageable level. A change officer should be named to oversee all changes to the scope of the project. Use your own change policy guidelines or Info-Tech's Business Requirements Change Request Template to help guide you. The chart below represents basic information that should be collected.

- Submit a Scope Change Request identifying the change, why it is needed, and who it directly affects.

- The Change Officer will present the change to the Project Sponsor to determine if the change will be accepted.

- Project Manager and Project Sponsor must sign off on the change proposal.

| Request # | Requested by | Brief Description | Sign Off |
| --- | --- | --- | --- |
| 021413.5 | Jim Dean | Include employee-owned devices in project scope. | Joe Smith |

7. High Level Risk Assessment

This area highlights some of the potential risks, and the measures that can be taken to avoid them. It is also advised to indicate who is responsible for monitoring and resolving these risks.

| Risk | Mitigation Measure | Responsibility |
| --- | --- | --- |
| Time Constraints may slow deployment | - Prepare a realistic timeline and make all possible effort to stick to it. - Consider hiring consultants if needed |  |
| Existing software products may not integrate with solution | - Identify integration issues and workarounds as soon as is possible - Consider seeking funding and sourcing a new compatible software product if needed |  |
| Impact on back end servers, storage, switches and network computing may be more than expected | - Perform an impact assessment as soon as is reasonable - Consider securing funding and resources for upgrades if needed |  |
| End users may be reluctant to embrace the change | - Provide ample opportunities for training, both formally and informally - Continuously stress the benefits that VDI brings to end users |  |

8. Key Deliverables

Each deliverable does not necessarily have to be listed. Deliverables key to project success or those that have associated issues that need to be addressed at the start of the project should be documented. Below are some examples:

| Item | Key Deliverables |
| --- | --- |
| 1. | Requirements Document |
| 2. | RFP for thin clients and tablets |
| 3. | Communication Plan |
| 4. | Training for IT Staff |
| 5. | Training for new users |
| 6. | Handover Instruction |
| 7. | New Technical Standard(s) |
| 8. | New Procedures |
| 9. | New Roles and Responsibilities |

Milestones (Interim Deliverables):

Important milestones and their target dates should be recorded here to help keep the project on track.

| Item | Milestone | Target Date |
| --- | --- | --- |
| 1. | Start Date |  |
| 2. | Gather requirements |  |
| 3. | Select Vendor |  |
| 4. | Proof of Solution |  |
| 5. | Staff Training |  |
| 6. | Pilot set-up |  |
| 7. | Monitor and Assess Pilot |  |
| 8. | Closure Date |  |

9. High-Level Budget

This is the estimated amount of money and other resources (e.g. user time) required for the project.

ITS’ funding amount available for this project is: $ XXX ITS’ allocated time for this project is: X days

The project budgeted allocation does cover: - The purchase of 30 thin clients - IT time allocated towards communication and training efforts

The project budgeted allocation does not cover: - IT overtime - Any costs related to applications that do not function correctly with VDI

[Insert results from Desktop Virtualization TCO Calculator ]

10. Lessons Learned and Modifications

This section should be completed after the pilot implementation, in order to summarize successes and failures and to determine the best strategy to continue into full-scale implementation. The project charter - as a living document - should also be updated to be used as an implementation charter. Incorporate the results from the VDI Pilot Test Assessment Template and this Lessons Learned section to increase the probability of a successful implementation.

| Successes | Implications |
| --- | --- |
| Users reported that there was not a significant change in the performance of their workstation | The VDI solution was successful and should be scaled up accordingly |
| The time it takes to resolve a helpdesk ticket for those on VDI has decreased | Implementation should decrease helpdesk response time in the long-run |

| Failures | Implications |
| --- | --- |
| Users were reluctant to let go of their PCs | The user benefits of VDI will need to be better communicated. We may also want to look into investing in larger monitors to counteract the sense of loss. |
| Several applications did not work correctly on VDI | IT will have to look into alternatives solutions to handle these applications, or remove the people that use these applications from the VDI implementation. |

11.  Projected Timeline

This table should be used as a high-level view of the lifecycle of the implementation, in order to keep the project on track. It should be modified as new issues arise, processes are streamlined, or organizational makeup changes. More granularity can be documented in the Milestones section above.

| Year | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| 2013 | Stage 1 rollout to Finance - 40 FTEs |  | Stage 2 rollout to Marketing, PR, and Level 1 Sales - 100 employees | Stage 3 rollout to Level 2 and 3 Sales - 100 employees |
| 2014 | Reassess viability of BYOC program with focus group | Stage 4 rollout |  |  |
| 2015 |  |  |  |  |

Info-Tech Research Group tools and template documents are provided for the free and unrestricted use of subscribers to Info-Tech Research Group services. These documents are intended to supply general information only, not specific professional or personal advice, and are not intended to be used as a substitute for any kind of professional advice. Use this document either in whole or in part as a basis and guide for document creation. To customize this document with corporate marks and titles, simply replace the Info-Tech Information in the Header and Footer fields of this document.